## Slide 1: Corporate Plans for 2021-22

## Slide 2
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
Developing Borough level estates plans and strategy
Supporting local service transformation, CMHT, PCNs
New Service Developments
Develop capital plan and schemes and financial scope
Value
Collaborating with Digital dept to upgrade estates
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Singe Mile End Site Plan – one borough inpatient site (TH & CH) & MHCOP centre of Excellence
Capital Plans development
estates optimisation and redesign
Estates
Developing Neighbourhood model across Hackney
Bedford Village re-provision
Pharmacy and PPE storage plans
Business Case to expand Moorgate ward
Redesign/relocation of Passmore Edwards
Strategic Objectives
Secondary Drivers
21-22 Priorities
Service User Outcomes

## Slide 3
Estates
No. | Top Key Priority Areas (Estates) | Milestones | Local Leads | What Cooperate /DMT support is required | Expected Delivery Dates
1 | Capital Plans Development | Clarify successful bids and investment envelope for next year Agree priority projects and schemes Sign off and build capital plan | Borough Directors | Finance, Executive Decision | 12 months
2 | Bedford Health Village Re-provision | Scheme currently in progress | Eugene Jones/Richard Fradgely | Finance, Executive Decision | 36 months
3 | Moving out of Passmore Edwards to First Avenue | Scheme Currently working progress | Bailey Mitchell | Finance, Executive Decision | 18 months
4 | Single Mile End Site – One Borough inpatient site (Hackney and Tower Hamlet’s) MHCOP centre of Excellence | Scheme yet to be confirmed – transformation project leads currently scoping | Richard Fradgely | Finance, Executive Decision | 5 years
5 | Pharmacy and PPE Storage Space | Develop clear estate strategy for one storage solution, or multiple sites to manage increased demand Looking for premises Commercial Appraisal of options, Financial viability on selling medication to other providers | Jenny Melville /Amy King | Finance, Pharmacy, CDD, Executives Decision, Digital, Corporate Nursing | 3- 6 month (decision on approach)
6 | Business case to expand single person facility in Moorgate Ward | Increase ward to 4-5 medium secure wards Agree Business Case | Phil Baker / Sarah Barnett | CDD, Finance, Lawford, Tony, Estates | 12 months
7 | Local Service Transformation Work | Various service level initiatives under way such as Community Transformation, Service redesign | Borough Directors | DMT’s | 12 months
8 | Developing Borough Level Estate Strategies | Reappraisal of Estates utilisation Working with Digital and DMTs to appraise future working practices and estates needs | Borough Directors/ John Hill/ Philippa Graves | Borough Directors, Clinical Directors, Digital, Finance , Estates | 12 months

## Slide 4
Access, Demand, Capacity
Digital Models of Care`
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
Staff survey results and delivery of plans
Trust-wide rollout of Health eRoster, embedding into routine business
Setup central Staff Bank Service to integrate across ICS, establish central booking team and app
New Service Developments
Sustain our COVID services and support
Delivering training required for vaccine pods – 3 across Trust
Deliver new Learning Management system – training Academy
Value
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Expanding OD offer across the Trust and teams
Maintaining focus on Staff Inequalities across Trust
FV programmes, remote working, reduced travel & conference expenses, printing savings, increased digital service offers and less DNAs, estates rationalisation, procurement
People & Culture
Anchor employer – recruiting locally
Brexit Planning
Develop and deliver leadership offer for the trust
Implementation of respectful resolution pathway, reduce use of formal processes
Realigning P&C senior leadership team to support primary care and increase OD capacity
Converting Integrated Care competencies into a tool
Increase coaching and mentoring capacity in the Trust
Strategic Objectives
Secondary Drivers
21-22 Priorities
Statutory & Mandatory Training – Focus on returning to >90% Compliance
Create additional opportunity for new and existing apprenticeship pathways
Support for change activities and new service integration
Create and deploy talent management processes
Service User Outcomes

## Slide 5
People & Culture
No. | Top Key Priority Areas (P&C) | Milestones | Local Leads | What Directorate support is required | Expected Delivery Dates
1 | Trustwide rollout of Health eRoster | Getting all teams onto eRoster and optimising the platform and embedding into business as usual Training and support offered to DMTs Establish real time reporting for sickness /absence | Archana Saanap | All DMTs to adopt new system Informatics | 18 months
2 | Setup central Staff Bank Service to integrate across ICS | Establish central booking team, and app to improve service delivery, train staff to use new processes and embed practices | Irfaan Ibne | All DMTs to adopt new system | 6 months
3 | Deliver training required for vaccine pods - 3 across the Trust | Recruit and train staff , establish pods and advertise for vaccinations Commence delivery vaccinations for the public | Irfaan Ibne | Corporate Nursing | 3 months
4 | Delivering New Learning Management system – training Academy | Procure new system, develop content and embed across DMTs One stop shop for all training needs established | Steve Palmer | All DMTs to develop content for local needs | 12 month
5 | Realigning P&C senior leadership team to support primary care and increase OD capacity | Review completed to align to primary care needs | Tanya | Primary Care Directorate | 3 month
6 | Implementation of respectful resolution pathway | Reduced formal processes for reconciliation Increased informal resolutions Communication of service to DMTs | Corinne Cunningham | All DMTs to adopt new system | 6 month
7 | Maintain focus on Staff Inequalities across the Trust | Delivery of the people plan, debias recruitment Maintain the focus on Race & Privilege across the Trust Supporting the work of all staff networks | Tanya Carter | All DMT to feedback on progress | 12 month
8 | Staff Survey Results and plans to be mobilised | Analyse new staff survey results, distribute to teams to develop action plans and monitor progress | Jill Dabbs | All DMTs | 6 months
9 | Brexit Planning | Ensure are Eu workforce have a settled status, ensure all new recruitment is compliant with immigration rules | Isabella Larkin |  | 6month
10 | Anchor employer – recruiting locally | Shifting recruitment strategy to recruit locally and reduce unemployment in London Building local partnerships and talent pool Deploy values-based recruitment policy Work experience opportunities | Jemma Ball | DMTs to adopt new values-based recruitment policy | 12 month

## Slide 6
People & Culture
No. | Top Key Priority Areas (P&C) | Milestones | Local Leads | What Directorate support is required | Expected Delivery Dates
11 | Sustain our COVID services and support | Maintaining staff wellbeing, testing and support across the Trust, learning from what’s worked well from pandemic | Bernadette Fitzharris |  | 6 months
12 | Develop and Deliver Leadership offer for the Trust | Resource agreement from exec Delivery of short-term offer Scoping/agreement of long-term offer | Donna Willis |  | 12 months
13 | Expanding OD Offer to all teams in the Trust | As resources allow, work with localities to support team behaviours and performance | Donna Willis |  | 12 months
14 | Converting Integrated Care Competencies into a tool | Subject to funding, test the competencies with a wider population Develop an online platform to enable utility at individual, team, organisation and system level. | Donna Willis |  | 12 months
15 | Increase coaching and mentoring capacity in the Trust | To establish further development of coaching skills within the Trust To fully launch the coaching and mentoring platform | Olga Osokina |  | 6 months
16 | Statutory & Mandatory Training – Focus on returning to >90% compliance | Create a trust wide and locality specific plan to focus on priorities Deliver programme of training to achieve target | Princess Kabba | All DMTs | 8 Months
17 | Create additional opportunity for new and existing apprenticeship pathways | Provide support to professional leads and functional teams to increase the accessibility and availability of apprenticeships | Sarah Canning | All DMTs, Professional Leads | 12 Months
18 | Support for Change Activities and new service integration | Provide support to DMTs and services when making organisational changes and creating new services Work to better define the process for new services to ensure P&C engaged before process finalisation | Tanya Carter / Shefa Begom | All DMTs, BDU | 12 Months
19 | Create and deploy talent management processes | Create talent definition and mapping processes that highlight and support the development and progression of key talent | Steve Palmer | All DMTs | 12 Months

## Slide 7
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
To increase the number of service users and carers in full or part-time employment/education
Co-producing everything we do
New Service Developments
Value
Empowering people digitally – access to technology and the confidence and skills using it. ELFT to develop a truly meaningful digital offer for service users, carers and staff
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
The Trust to demonstrate work in improving inequalities – i.e. Black Lives Matter, LGBTQ+, poverty, cultural awareness..)
FV programmes, remote working, reduced travel & conference expenses, printing savings, increased digital service offers and less DNAs, estates optimisation, procurement, LD unit, LBH Savings
People Participation
Improving our signposting into voluntary sector and community based opportunities (i.e. sports, hobbies, financial support..)
Service users and carers to be referred into People Participation at the start of their journey with ELFT
COVID-19 challenge – People Participation have been useful in terms of connections with service users and carers, addressing loneliness, physical exercise and connecting people, for example Befriending service. Share learning with teams across the Trust.
Strategic Objectives
Secondary Drivers
21-22 Priorities
Service User Outcomes
Improving physical health, loneliness, relationships, signposting to VCS & community opportunities, rollout DIALOG across all services
Supporting carers, service users into employment & education

## Slide 8
People Participation
No. | Top Key Priority Areas | Milestones | Local Leads | What Directorate support is required | Expected Delivery Dates
1 | ELFT to support the expansion and development of education and training led by people with lived experience – education of staff and of service users. |  |  |  | 
2 | To increase the number of opportunities for service users and carers to be in full and part time employment/education. |  |  |  | 
3 | Service users and carers to be referred into People Participation at the start of their journey with ELFT |  |  |  | 
4 | Empowering people digitally – access to technology and the confidence and skills using it. ELFT to develop a truly meaningful digital offer for service users, carers and staff. |  |  |  | 
5 | Co-production in everything we do. |  |  |  | 
6 | Improving our signposting into the voluntary sector and community based opportunities (i.e. sports, hobbies, financial support…) |  |  |  | 
7 | The Trust to demonstrate work in improving inequalities – i.e. Black lives matter, LGBTQ+, poverty, cultural awareness… |  |  |  | 
8 | Covid-19 challenge – People Participation have been useful in terms of connections with service users and carers, addressing loneliness, physical exercise and connecting people, for example Befriending service. Share learning with teams across the Trust. |  |  |  | 

## Slide 9
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
Rio Mobile App, digital dictation - ongoing & BAU
ELFT Record Viewer 2 -3 year project
Trust integration Engine – 2 year Project
New Service Developments
New service desk portal
Imprivata – single sign on – after VDI – Yr 2
Value
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Digital Champions/ Expert User Network, training and support – Yr 1 – BAU after
Scaleable architecture - ongoing
Agile working, secure & robust platforms, efficient view of the user record from anywhere, quality of service & support
Delivered, Pt enabled to manage care digitally, Green footprint improved
Estates & Digital Collaborative – fit for purpose sites – 3-5 year programme requires funding – GDPR & VfM delivered on contracts
DIGITAL – 3 YEAR PLAN
BLMK architecture – linking up record -2-3 year project
People Participation input Digital team and workstream including digital Citizen Record for BLMK & NEL – all 3 years
Cyber security and education – Yr 1 – BAU after
Service enabled scalable profiles supporting any device - 2 year project – requires ongoing funding
DIGITAL DIRECTORATE – GETTING THE ESSENTIALS RIGHT.
Strategic Objectives
Secondary Drivers
21-22 / 23 - 24 Priorities
Digital Solutions Board Implementation - followed by DOTB
Electronic Observations – 2 year project
Virtual SmartCards – after Mobile supported by NHS X – 2 year
CMHT Transformation – NEL only
Bedfordshire Health Village
Service User Outcomes
Year 1
Year 1 & 2
Year 1 & 2 & 3 +

## Slide 10
Digital – 3+ Year Plan
No. | Top Key Priority Areas (Newham) | Milestones (Definition of Done) | Local Leads | What Cooperate support is required | Expected Delivery Dates | Year 1-2 | Year 3-5 | Green Agenda/ Efficiency | Funded
1 | Scalable Architecture | All aspects of ELFT architecture achieve Kite Mark, are resilient, sized correctly and resilient. | CTO/CDO | Funding – linked to Strategy & some DA funding – IaaS, DaaS, Networks, Data Links | 1-2 | √ | √ | √ | Part
2 | Trust Integration Engine | All key systems integrated so data entered only once. | CTO/CDO | Funding – linked to Strategy – year 1 DA programme | 18 months starts in June 21 – Digital Aspirant. | √ | BAU | √ | Year 1 only
3 | Citrix Cloud deployable | All devices supported by VDI – no delay in spinning up new users. | CTO | Funding – linked to business case – Pilot funded by DA | 1 – 2 years. Dependent on deployment methodology. | √ | Business Case | √ | Only Pilot DA
4 | Service enabled scalable profiles supporting any device | Key profile & apps defined by business to support new starter process. | CTO/CDO | As above. Directorate level and transparent costing. | As above. | √ | √ | √ | Only Pilot DA
5 | Cyber Security & Education | CTO in place CISO in place NHS X compliant | CDO/CTO/ CISO | Board support & Directorate engagement – outlined in the Strategy | 1 year | √ | √ | √ | Year 1 Only – in the Strategy
6 | New Service Desk portal | Ability to reset passwords on line | SDM/CPM | New tools to support self-service application | 1 – 2 years - DAF | √ | √ | √ | √
7 | Imprivata – single sign on – follows VDI and supports virtual smartcards | Enabled login to support virtualised applications. NHS X dependent | SDM/IDM | New user interface – supports virtual smart card | 8 months – 2 years – NHS X dependent | √ | √ | √ | Business case needed
8 | ELFT Record – requires 2/3/4/5/7/8 | One pane of glass to access the key record entries for user ease. | IDM/CTO/CCDO/CDO | User input for configuration | 3 – 5 years for all services. | √ | √ | √ | Funding needed
9 | - Dictation -RIO mobile | Ongoing DMT based projects – review of Definition of Done occurring. | CPM/CCIO | User input for configuration | DMT specific – funding expires this year. | √ | √ | √ | Specific project stood up for this.
10 | PP Input – getting the most out of Digital Citizen Record | 3 year programme – end point is citizens in NEL & BLMK being able to manage their own record. | IDM/SDM/PMO | User & DMT input & Patient Participation - Linked to Patient held record in BLMK & NEL. Must Do. DA starts it only. | 2-3 years – but starting in January. | √ | √ | √ | Needs on going funding

## Slide 11
No. | Top Key Priority Areas (Newham) | Milestones (Definition of Done) | Local Leads | What Cooperate support is required | Expected Delivery Dates | Year 1-2 | Year 3-5 | Green Agenda/Efficiency | Funded
11 | Virtual Smart Cards – NHS D approved platform – Priority 3 & 7 must be delivered first. | All compatible devices will support virtualised smart cards. | SDM/IDM/CTO | Virtualise smart card function – following 3 & 7. | Up to 3 years + - NHS X dependent. | √ - Yr. 2 | √ | √ | Business case needed
12 | Electronic observations rollout across the Trust | All pt obs are collected into the RIO platform for in patient areas. | TB/CCDO/IDM/SDM/CTO/COO/DoN | To improve safety and quality across the Trust | 18 months for all services – 6 months plan & 12months roll out. | Start roll out Oct 2021 √ | √ | √ | Eobs only funded by DA- finance needs to be profiled.
13 | Establish and support Solutions Board approach to all Digital Projects to ensure fair and equitable decisions, funding, resource, and prioritisation to digital programmes. | Proper oversight and inclusive decision making and prioritising the limited digital resources. | COO/CDO/CTO/Business Leads & CTO | Outline plans and paperwork being incepted to ensure robust approach to Digital projects | 1 year to make fully established | √ | √ | √ | No funding required
14 | ICS architecture – linking up record | ELFT staff can see record from all providers in NEL or BLMK | CDO/CTO/IDM | Time to build required architecture & funds – a must do – not optional. | Over the next 5 years. NEL & BLMK | √ | √ | √ | Only first part funded – essential for ICS.
15 | Estates & Digital Collaborative – Fit fir Purpose | Every ELFT owned site has a Digital Kite mark for quality and a standard for estates that meets needs. | CTO/IDM/AD.Est. | Full site survey & assessment. Funding to address shortfalls. New Ways of working described. Must Do. | 5 years – 127 sites to address. Priority 1 sites within 12 months from decision. | √ | √ | √ | Requires full funding
16 | Digital Champions / Expert User Networks Training and support PP & Exclusion | All DMT’s have an identified Champion & standardised usage across Trust. | CCDIO/PP lead | All DMTs have Digital Champions. |  | √ | √ | √ | Funding will be needed.
17 | Community Service Transformation/ Community Mental health Transformation | Project still being defined – will update when known. | SDM/PM/IDM/CCDO | Pilot & rollout of new platforms & forms for Community Transformation | NEL only funded to £424K – BLMK not funded. Separately funded project. | √ | √ | √ | NEL funded – Year one only. BLMK funding needed.
19 | Bedfordshire Health Village | New SOTA facility stood up fully digitally enabled. | CTO/IDM/CCDO | Planning & Delivery of a Digital First health care facility for ELFT in BLMK | Will need a PM & resources going forward to delivery the plan & implementation | √ | √ | √ | Funded by Capital but needs business case.
Digital : 3+ Year Plan

## Slide 12: ELFT Digital Strategy – Deployment Plan 2020/21/22/23/24 – Page One
Scheme (Project) | 2020-21 Q2 | 2020-21 Q3 | 2020-21 Q4 | 2021-22 Q1 | 2021-22 Q3 | 2021-22 Q4 | 2022-23 Q1 | 2022-23 Q2 | 2022-23 Q3 | 2022-23 Q4 | 2023-24 Q1 | 2023-24 Q2 | 2023-24 Q3
1. TIE - 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
2. Wi-Fi & Networks -15 |  |  |  |  |  |  |  |  |  |  |  |  | 
3. VDI/Citrix Cloud -3 |  |  |  |  |  |  |  |  |  |  |  |  | 
4. Digital Profiles - 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
5. CYBER - 5 |  |  |  |  |  |  |  |  |  |  |  |  | 
6. Service Desk Portal - 6 |  |  |  |  |  |  |  |  |  |  |  |  | 
7. Virtual Smart card - 11 |  |  |  |  |  |  |  |  |  |  |  |  | 
8. E-Observations -12 |  |  |  |  |  |  |  |  |  |  |  |  | 
9.Patient Held Record |  |  |  |  |  |  |  |  |  |  |  |  | 
10. Single Sign On/Impravata |  |  |  |  |  |  |  |  |  |  |  |  | 
11. SHCR - BLMK |  |  |  |  |  |  |  |  |  |  |  |  | 
12. Solutions Board -13 |  |  |  |  |  |  |  |  |  |  |  |  | 
PILOT
Remediation
SCOPING
TO DECIDE ON PRIORITIES
CYBER IMPROVEMENT PROGRAMME
RELIES ON VDI/NHS X CONTRACT
Scoping/Planning/Roll out to all Patients – 2 PROJECTS ONE BLMK & ONE NEL
AFTER TIE
PLANNING & IMPLEMENTATION
ONGOING IMPROVEMENT PROGRAMME PART OF CAPITAL PROGRAMME IN PARTNERSHIP WITH ESTATES
SELF SET PASSWORDS
SCOPING
IN PARALLEL WITH THE TIE IMPLEMENTATION
BAU
DELIVERY
BAU
BAU
TRUST WIDE ROLL OUT
BAU
COST FOR USE/BENEFITS
UPGRADE
COST FOR USE/BENEFITS
BAU
BAU
BAU
COST & PLAN

## Slide 13: ELFT Digital Strategy –Deployment Plan 2020/21/22/23/24 – Page Two
Scheme (Project) | 2020-21 Q2 | 2020-21 Q3 | 2020-21 Q4 | 2021-22 Q1 | 2021-22 Q3 | 2021-22 Q4 | 2022-23 Q1 | 2022-23 Q2 | 2022-23 Q3 | 2022-23 Q4 | 2023-24 Q1 | 2023-24 Q2 | 2023-24 Q3
13.Comm.Health.Transfomation Comm. Mental H Transformation |  |  |  |  |  |  |  |  |  |  |  |  | 
14. Bed.Health.Village |  |  |  |  |  |  |  |  |  |  |  |  | 
15. IAAS & Data Links – 1 |  |  |  |  |  |  |  |  |  |  |  |  | 
16. ELFT Record – 8 |  |  |  |  |  |  |  |  |  |  |  |  | 
17. RIO Upgrade – 1st |  |  |  |  |  |  |  |  |  |  |  |  | 
18. Digital Transformation Operational Board |  |  |  |  |  |  |  |  |  |  |  |  | 
19. People Participation |  |  |  |  |  |  |  |  |  |  |  |  | 
20. Digital Champions |  |  |  |  |  |  |  |  |  |  |  |  | 
1ST of TYPE RIO UPGRADE
NEL Only
SCOPING/BC/BLUE PRINTS
DELIVERY
BAU
COMPLETE TRANSITION & RESILIENCE
SCOPING & SOLUION CHOICE
BAU
INCEPTION
CHAIRED BY OPERATIONS
SUPPORTING DIGITAL FIRST ON THE SHORT FLOOR
INCLUSION & DIGITAL POVERTY
Transforming Mental health digital approaches

## Slide 14
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
Support system planning through the development of Integrated Care Systems through new contract arrangements and governance systems
New Service Developments
Develop new contract structure to support the development of Compass and Third sector offer
QI project – redesign processes from contract sign off to mobilisation & implementation to offer greater support to DMTs
Value
Workforce, Equality & Diversity
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Support FV programmes through review of future estates requirements and QI project to reduce waste between CDD and finance processes and reduce time from business case concept to recruitment
Commercial Development
Complete contract negotiations for 21/22 and 22/23 (subject to national guidance)
Work in collaboration with DMTs and CCGs to develop operational plans for 21/22 and 22/23 and ensure delivery of LTP requirements and surge planning following COVID.
Support DMTs with managing emerging external system pressures on Directorates resources including the Trust KPI review and developing contract and governance arrangements that are streamlined
Estates
Support DMTs with emerging business case requirements including responding to the COVID recovery and business cases to support LTP delivery requirements
Provide contractual and business development support for the establishment of new services and systems including the NCEL CAMHS provider collaborative and Primary Care
Develop ELFT as an anchor institution through revised procurements and tendering systems
Accreditation for delivery of NHS procurement standards
Develop team and staff capability through training programmes including CIPS (procurement), QI, Leadership
Strategic Objectives
Secondary Drivers
21-22 Priorities
Service User Outcomes

## Slide 15
Commercial Development
No. | Top Key Priority Areas (CDD) | Milestones | Local Leads | What Cooperate/DMT support is required | Expected Delivery Dates
1 | Support system planning through the development of Integrated Care Systems through new contract arrangements and governance systems | Subject to national guidance on the new operating model CDD will be required to support the development of new contractual arrangements and governance systems . | Mohit Venkataram/Richard Fradgley /Robin Campbell | DMTs/Finance/Informatics/Performance/Estates/ Integrated Care Systems stakeholders (joint working) | Ongoing throughout 2021/22
2 | Develop new contract structure to support the development of Compass and Third sector offer | Set up new sub contracting process for VCSE activity via Compass (June 2021) | Mohit Venkataram/Robin Campbell | DMTs/Finance/Compass | 3 months (Completed by June 2021)
3 | QI project – redesign processes from business case concept to contract sign off to mobilisation & implementation to offer greater support to DMTs | Establish Qi Group (April 2021) Agree scope of QI project, complete driver diagram and submit to Qi forum for project initiation (May 2021) Undertake detailed process mapping (June 2021) Begin PDSA cycle for core project deliverables (July 2021) Complete implementation and review (Dec 2021) | Robin Campbell | Finance / CDD team / IMT | 9 months (Dec 2021)
4 | Provide contractual and business development support for the establishment of new services and systems including the NCEL CAMHS provider collaborative and Primary Care | Provide ongoing support including the establishment of the PCN prospectus (Initial version by April 2021 and future versions throughout 2021 as the ELFT offer develops) Support 21/22 NCEL contracting and support development of Phase 2 collaborative (subject to national guidance) | Mohit Venkataram/Robin Campbell | Primary Care DMT / NCEL CAMHS DMT / Finance/ Estates / Qi / HR / informatics / | Ongoing in 21/22
5 | Negotiation of 21/22 and 22/23 contracts (subject to yet to be published NHS operating framework for next year). This includes Mental Health Investment (22/23 investment brought forward to 21/22) standards and out of hospital community services. | Review existing contract indicators (end of Jan 2021). Setup planning meetings with CCGs (April 2021) Agree priority investment and priority areas (April 2021) Agree Contracts subject to national operating framework (June 2021) Process to be repeated December next year for 22/23 planning round | Mohit Venkataram/Richard Fradgley /Robin Campbell | DMTs/Finance/Informatics/Performance/Estates/ Integrated Care Systems stakeholders (joint working) | 1 month (Completed by April 2021)
6 | Develop team and staff capability through training programmes including CIPS (procurement), QI, Leadership | Ensure staff from each sub team are enrolled on Qi training programme (throughout 21/22) Ensure all procurement staff are CIPS trained or equivalent throughout 21/22) Support staff to access leadership programmes inc NHSE | Robin Campbell / Steve Newton | CDD team | Ongoing throughout 2021/22
7 | Support DMTs with managing emerging external system pressures on Directorates resources including the Trust KPI review and developing contract and governance arrangements that are streamlined | Review existing contract indicators and agree with CCGs (end of June 2021) Agree future contract management architecture (subject t o national guidance) | Mohit Venkataram/Richard Fradgley /Robin Campbell | DMTs/Finance/Informatics/Performance/Estates/ Integrated Care Systems stakeholders (joint working) | 3 months (Completed by June 2021)
8 | DMT Business Cases and bids | Responded to Long Term Plan and COVID recovery / surge business case requirements and specific service developments across Mental Health, Community Health and Primary care services. | Robin Campbell/Mohit Venkataram | DMTs/Finance/Informatics/Performance/Estates/Integrated Care Systems stakeholders (joint working) | 12 months

## Slide 16
Commercial Development
No. | Top Key Priority Areas (CDD) | Milestones | Local Leads | What Cooperate/DMT support is required | Expected Delivery Dates
9 | Support FV programmes through the procurement programme and the Business cases in MHIS | Procurement programme throughout he year as per plan Delivery of MHIS ad business cases in line with operational planning timescales | Robin Campbell / Steve Newton | CDD team / Financial Viability / Finance / Estates / IMT | Ongoing throughout 2021/22
10 | ELFT as an Anchor | Agree a set of metrics and scoring methodology [across addressable categories]: Key areas: Employment and Training, Equality and Diversity, and Sustainability. Appoint a Social value System: To have interoperability to etendering system with the option to support the evaluation and ongoing contract management. Develop and test documentation: Primarily in tenders and mini competitions for individual Trusts and collectively. Develop a standard set of KPI’s: To thread the metrics into contract management | Steve Newton/Mohit Venkataram/Richard Fradgley | Integrated Care Systems in particular NEL STP stakeholders | 3 months (completed for June)
11 | NHS Procurement Standards https://www.gov.uk/government/publications/nhs-procurement-standards | Run diagnostic tool to self test: Link with Finance for data. Apply for accreditation: Assessor to assess ELFT. | Steve Newton/Mohit Venkataram | Integrated Care Systems in particular NEL STP stakeholders | 2 months – Accreditation by May 2021

## Slide 17
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
Define and implement care processes (assessment and care planning) and specific pathway offers
New Service Developments
Further develop our relationships and processes for work with VCSE organisations, review and renew community connector
Value
Deployment of community EMIS in PCN blended teams
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Development and delivery of workforce plan, including development within new role, competency framework
FV programmes, remote working, reduced travel & conference expenses, printing savings, increased digital service offers and less DNAs, estates optimisation, procurement
Shaping future service models
CMHT Transformation
Further embedding of co-production within design and delivery of new care model
Delivering Local Borough of Hackney Saving Plans
Procurement of community connectors across East London
Develop evaluation approach
Formalise team structural arrangements
Strategic Objectives
Secondary Drivers
21-22 Priorities
Service User Outcomes

## Slide 18
No. | Top Key Priority Areas (MH Transformation) | Milestones | Local Leads | What Corporate support is required | Expected Delivery Dates
1 | Deployment of Community EMIS in PCN blended MH teams | Safety testing (?3 months) Deployment for testing in Newham (?3 months) Wider roll-out (?6 months) | Peter Macrae Warren Reynolds *TBC | Infrastructure funded through programme slippage, Digital, informatics | TBC
2 | Define and implement care processes (assessment and care planning) and specific pathway offers | Workshops and learning sets (3 months) Pulling together in programme library (3 months) | Various Jamie Stafford | N/A | May 2021
3 | Development and delivery of workforce plan, including development within new role | Developing competency framework for CMHT Transformation Workforce | Lucy Ingle | TBC | 6 months
4 | Further embedding of co-production within design and delivery of new care model | Increased focus on participation (throughout 6 months) | Becky Derham and People Participation Workers | People Participation | Continuous
5 | Formalise any structural team changes | Design of formal approach (3 months) Deliver likely to be May 2021 | Lucy Ingle and P&C BPs | P&C Business Partners (Lucy to coordinate) | June 2021
6 | Develop Evaluation approach | Define parameters of Evaluation across Consortium of EI sites (3 months) Scope and procure partner for external impact evaluation (3 months) | Jennie Parker Jamie Stafford | Procurement support to identify impact evaluation partner | June 2021
7 | Further develop our relationships and processes for work with VCSE organisations | Review and extension of Community Connector contracts (3 months) Develop mechanisms to support future work Procurement of Community Connectors across East London | Justin Phillips Compass | BDU support, Procurement | August 2021
CMHT Transformation

## Slide 19
Access, Demand, Capacity
Digital Models of Care`
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
New Service Developments
Value
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Quality Improvement
Triple Aim projects:
Service Users with a BMI of 40 and over, living in Newham, who are housebound (Community Health Newham);
Adults who use illegal drugs and have acute mental health issues in Hackney, Bedfordshire, Tower Hamlets and Newham (Forensics)​
People aged >65 registered Leighton Buzzard population with moderate or severe frailty or Mild Cognitive Impairment (MCI) or diagnosed dementia with two or more underlying physical health long term conditions. (Bedfordshire CHS and Adult MH)
​Improving health outcomes for homeless people living in Tower Hamlets' hostels (Tower Hamlets Adult MH)
To improve quality of life for those living with LD across the populations the Trust serves (Learning Disabilities)
​To improve quality of life for those presenting crisis 5 or more times in 12 months (Newham Adult MH)
Reducing inequalities in accessing talking therapies for men in Bedford over 40 of Asian or Asian British ethnicity​ (Bedfordshire IAPT)
Improving healthcare for Unaccompanied Asylum-Seeking Children under the care of the local authority (SCYPS)
Enjoying Work programme, recuperation.
Service User Wellbeing Projects:
Improving awareness and understanding about the impact of racism
Service user involvement in staff interviews project.
Increasing service user empowerment in recovery through self-administration of medication.
Increasing the number of service users and carers involved in People Participation
Increasing Service User Engagement with Ward Activities as part of the Trusts strategy to Improve Service Users Experience of care.
Value learning system QI projects:
Reducing salary overpayments and taxi spend (Corporate)
Reduce spend , reduce time spent with SU in observation (Forensics)
Reduce number of face-to-face referral (Beds CH)
Reduce spend, Increase video consultations, reduce waiting time (Beds Adult MH)
Reduce waiting lists (Specialist Beds wellbeing)
Maintaining and building quality improvement skills and capabilities
Strategic Objectives
Secondary Drivers
21-22 Priorities
Masterclass on access, demand and capacity.
Flow QI projects:
Improving the flow in the Memory Assessment Service pipeline (Bedfordshire Adult MH)
Improving access to the Integrated Learning Disability Service (LD Hackney)
Equal Access to Tower Hamlets Early Intervention Service Psychology (Tower Hamlets Adult MH)
Optimising Integrated Discharge Pathways in the Integrated Discharge Hub (Tower Hamlets CHS)
Service User Outcomes

## Slide 20
No. | Top Key Priority Areas (QI) | Milestones | Local Leads | What Corporate support is required | Expected Delivery Dates
1 | Triple Aim | Choosing a population segment Identifying assets and needs Create a governance structure Develop change theory Create a set of Triple Aim measures Testing Changes Implementation Quality Control Scale-up and spread | QI Department Lead – Auzewell Chitewe Leighton Buzzard (Allison Jones and Julia Mead​) Learning Disabilities (Sanjay Nelson, Ruth Cooper) Newham MH (Ed Lander/Dominic Dougall) Forensics (Dr Abu Shafi) CHN Newham (Anthony Edwards) Tower Hamlets MH (Che Rosebert) SCYPS (Sveta Alladi and Jacqueline Simmons) IAPT Bedfordshire (Sharon Gugerly​) *Additional local projects can start throughout the year | QI (Learning system and project support) Informatics (data and EPR) Public Health (population needs data) Communications (promotion and recognition) Commercial Dev. Team (contracts) Exec Team (Sponsorship) All (Identifying opportunities for Triple Aim projects) Finance (value and costing) Quality & Performance (reports and data) | Multi-year
2 | Enjoying work | Identifying the quality issue Understanding the problem Developing a strategy and change ideas Testing Implementation and sustaining the gains | QI Department Lead (Auzewell Chitewe) SCYPS (Natalie Blanchard) Mental Health Law Team (Jasemine Ali) Newham CAMHS (Elaine Cheng-Whitehead) Quality compliance & Performance (Karamjeet Chana) Forensics Admin (Fiza Wafa) Bow ward (Elizabeth Hearn and Jo Gbongo) HealthE1 Homeless Unit (Marina Muirhead) TH CAMHS (Abdi-Karim Ibrahim) *Additional local projects can start throughout the year | QI (Learning system and project support) OD (OD interventions) People and culture (HRBP support) Communications (Promotion and recognition) Exec Team (Sponsorship) All (Identifying and encouraging own staff to start a project) | Multi-year Current phase: Sept 2022
3 | Value QI projects | May 2021 – launch Quarterly learning sessions October 2022 – End | Sarah Barnett Katherine Brittin | Informatics (data) All (Identifying opportunities for Value projects) Finance (costing) Communications (Promotion and recognition) Commercial Dev team (contracts) | October 2022
4 | Capability Building | ICP – Sept 20 – Feb 21 ILP - May - Sept2021 ICP – Oct 21 – Mar 22 ILP – Nov 21 – Mar 22 | Katherine Brittin (ICP) Auzewell Chitewe (ILP) | All (Identifying and encouraging own staff to attend training) Communications (Promotion and recognition) Finance (revenue and cost) Workforce (staff training data) | Multi-year. Current Phase: ILP - May - sept2021 ICP – Sept 20 – Feb 21
Quality Improvement

## Slide 21
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
New Service Developments
Value
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Informatics
Adoption of integrated Apps - CAMHS
Adoption of integrated Apps - CMHT
Adoption of integrated Apps - Perinatal
Adoption of integrated Apps - SCYPS
Faster access to overnight data for self-service dashboards
Improved responsiveness to adhoc data requests
Introduction of master patient index to link patients between main clinical systems (phase 2 DWH modernisation)
Inpatient DQH design (Phase 4 DWH modernisation)
Strategic Objectives
Secondary Drivers
21-22 Priorities
Service User Outcomes

## Slide 22
No. | Top Key Priority Areas (Informatics) | Milestones | Local Leads | What Cooperate support is required | Expected Delivery Dates
1 | Adoption of Integrated Apps - CAMHS | Development to be complete 31/5/2021 Adoption and training during June 2021 | Tom/Adnan/Forid | Support for communication of adoption and training. | June 2021
2 | Adoption of Integrated Apps – CMHT | Development to be Complete 30/4/2021 Adoption and training during May 2021 | Tom/Adnan /Forid | Support for communication of adoption and training. | May 2021
3 | Adoption of Integrated Apps – Peri Natal | Development to be Complete 31/3/2021 Adoption and training during April 2021 | Tom/Adnan /Forid | Support for communication of adoption and training. | April 2021
4 | Adoption of Integrated Apps - SCYPS | Development to be Complete 31/5/2021 Adoption and training during June 2021 | Tom/Adnan /Forid | Support for communication of adoption and training. | June 2021
5 | Faster access to overnight data for self-service dashboards | Reduction to 1pm Feb 2021 Noon end of Q2 2021/2 11am by end of Q4 2021/2 | Tom/Adnan /Forid |  | March 2022
6 | Improved responsiveness to ad hoc data requests | Average wait time to below 14 days by Q1 2021 | Tom/Adnan /Forid |  | June 2021
7 | Introduction of master patient index to link patients between main clinical systems (Phase 2 DWH Modernsiation) | Development begins Feb 2021 | Tom/Adnan /Forid |  | June 2021
8 | Inpatient DWH design (Phase 4 DWH Modernisation) | Development begins July 2021 | Tom/Forid | Support to sign off data models with stakeholders | Mar 2022
9 | Outpatient DWH design (Phase 3 DWH Modernisation) | Development begins December 2021 | Tom | Support to sign off data models with stakeholders | Summer 2022
Informatics & BI

## Slide 23
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
New Service Developments & Improvements
Value
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Financial Viability
Benefits Realisation of Community Mental Health Transformation
Reduce Paper Processes
Implement E-delivery Option for Service User Letters
Virtual Appointments, Meetings & Training
Improve quality/Reduce Cost of Non-Clinical Contracts
Optimisation of Existing Estates Portfolio
Improve Efficiency of Records Archiving Process
Develop New Approach to Future Estates Developments
Forensic Community Outreach Service Redesign
Forensic Low Secure Service Redesign
East Ham Care Centre Redesign
Learning Disability Assessment & Treatment Unit (partner with NELFT)
East London Neurodevelopmental Pathway
Reduced Staff Travel; Increased Agile Working
Corporate Process Redesign
East London-Wide Crisis Pathway Redesign
Luton & Bedfordshire Mental Health Rehabilitation Service Redesign
Reduce Luton & Bedfordshire Section 117 Spend
Improve Quality of North East London Mental Health Rehabilitation Placements
Tower Hamlets & Newham Community Health Services Merge
Benefits Realisation of Process Automation/Digitisation
Forensic Learning Disability Ward Expansion
Development of Single Points of Access to Improve Accessibility of Services
Develop Tailored Learning System for Value QI Projects
Develop a Value Section of Intranet
Implement Value Organisational Development Plan
Further Develop Sustainability/Value Relationship
Improve Quality of Service User Transport Through Development of Internal Transport Service
Strategic Objectives
Secondary Drivers
21-22 Priorities
Service User Outcomes

## Slide 24
No. | Top Key Priority Areas (Informatics) | Milestones | Local Leads | What Cooperate support is required | Expected Delivery Dates
1 | Development of Single Points of Access to Improve Accessibility of Services – IAPT and CAMHS | Scoping. As per DMT plans. | Sarah Wilson/Sarah Barnett | P&C | 3 months
2 | Improve Quality of North East London Mental Health Rehabilitation Placements | Identify funding, Appoint project team Develop 22-23 rehab plan | Shiraz/Sarah/Lucy Harrison | CDD | 1 month 3 months 6 months
3 | Forensic Learning Disability Ward Expansion | Redevelop ward space Cost modelling Implement marketing plan As per DMT plans. | Sarah/Tony Kasambira | CDD/Finance/Estates/Informatics | 6-9 months
4 | Forensic Community Outreach Service Redesign | Implement phase 2 redesign As per DMT plans. | Sarah/Phil Baker | CDD/Finance | 6 months
5 | Forensic Low Secure Service Redesign | Redesign ward team As per DMT plans. | Sarah/Phil Baker/Sian | CDD/Finance | 3-6 months
6 | East Ham Care Centre Redesign | Scoping As per DMT plans. | Eugene/Sarah | CDD/Finance/Estates | 6 months
7 | Learning Disability Assessment & Treatment Unit (partner with NELFT) | Scoping As per DMT plans. | Sanjay Nelson/Ruth Cooper/Sarah | CDD/Finance/P&C/PPG | 3-6 months
8 | East London Neurodevelopmental Pathway | To agree funding arrangements. Align resource to provide an East London service | Dominic/Sarah Dracuss/Shiraz/Sarah | CDD/Finance | 3-6 months
9 | East London-Wide Crisis Pathway Redesign | Analysis of time and motion study. Modelling of delivering services across the patch | Andrew Horobin/Ed Lander/Melanie King/Sarah | CDD/Finance/P&C | 3-6 months
10 | Luton & Bedfordshire Mental Health Rehabilitation Service Redesign Reduce Luton & Bedfordshire Section 117 Spend | Public Intentions Intender notice (PIN) Service Modelling Develop dedicated team for Section 117 | Michelle Bradley/Guy Thompson/Sasha Singh | CDD/Finance/P&C | 6 months
11 | Benefits Realisation of Community Mental Health Transformation | Scoping | Local CMHT Leads | Finance/QI/PPG | 9 months
12 | Benefits Realisation of Process Automation/Digitisation Reduce Paper Processes | Incorporate value considerations in digital projects. Re-negotiate Print supplier contract, provide head admin access to print portal, trustwide communications, QI project | Local service leads/Sarah | QI/Communications/P&C/IT | 6 months
13 | Implement E-delivery Option for Service User Letters | Run pilot with IAPT service. Develop plans for trustwide roll-out | Local service leads/Sarah | Communication/IT/PPG | 3 months
14 | Virtual Appointments, Meetings & Training | Audit of virtual contacts | Sarah/Local Leads | IT/PPG/Informatics | 6 months
15 | Reduced Staff Travel; Increased Agile Working | Analysing travel data (Audit of transport cost); Monitor impact on estate use | Sarah/Local service leads | Estates/IT/P&C/Informatics | 6 months
Financial Viability

## Slide 25
No. | Top Key Priority Areas (Informatics) | Milestones | Local Leads | What Cooperate support is required | Expected Delivery Dates
16 | Corporate Process Redesign | Establish corporate project team | Corporate managers/Sarah | All corporate teams | 6 months
17 | Improve Quality of Service User Transport Through Development of Internal Transport Service | Seek approval for review paper on recommendations, establish project team and implement plan on recommendations | Local service leads | P&C/IT/PPG/Estates/Procurement/Finance | 9 -12 months
18 | Optimisation of Existing Estates Portfolio Develop New Approach to Future Estates Developments | Develop template for analysing estates space utilisation, explore opportunities where leases are ending in 21-22. | Sarah/John Hill/Frank | Estates/IT/Finance | 12 months
19 | Improve quality/Reduce Cost of Non-Clinical Contracts | On going work, Identify opportunities where supplier cost can be reduced | Sarah/local services leads | CDD | 12 months
19 | Improve Efficiency of Records Archiving Process | Model options for record archive storage | Chris Kitchener/Sarah | IG/IT/Procurement | 6 months
20 | Further Develop Sustainability/Value Relationship | Develop plan to understand relationship between sustainability and value | Adam Toll/Sarah | Estates | 6-9 months
21 | Develop Tailored Learning System for Value QI Projects | As per QI project plan | Sarah/Auz/Katherine/Susan | QI | 3 months
22 | Value culture change work | Implement Value Organisational Development Plan Develop a Value Section of Intranet | Sarah/Steven Course/Lorraine | Communication/Finance/P&C | 3 months
Financial Viability

## Slide 26
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
New Service Developments
Value
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Public Health
Developing ELFT as a Marmot Trust
Inequalities Workstream
ELFT as an anchor organisation
Employment Steering Group
Increasing understanding of population health and improved use of data systems to address inequalities
NHS England Tobacco Control Early Implementer Site learning and embed across ELFT
Develop Evaluation/metrics approach
Strategic Objectives
Secondary Drivers
21-22 Priorities
Improving physical health, loneliness, relationships, signposting to VCS & community opportunities, rollout DIALOG across all services and improving outcomes
Service User Outcomes

## Slide 27
No. | Top Key Priority Areas (Inequalities workstream) population health) | Milestones | Local Leads | What Corporate support is required | Expected Delivery Dates
1 | Developing ELFT as a Marmot Trust | Establish the strategic approach to enable ELFT to become a ‘Marmot Trust’ and develop plan to bring this together in partnership with UCL Institute of Health Equity. |  | TBC | September 2021
2 | Inequalities Workstream | Continue to implement the inequalities driver diagram – focus on evaluation and measuring progress | Richard Fradgley Angela Bartley | TBC | Continuous
3 | ELFT as an anchor organisation | Develop ELFT as a leading anchor organisation focussing on local employment and embedding social value as a key part of our procurement work | Angela Bartley Steve Newton | Procurement Team P&C | 6 months
4 | Employment steering group | To increase the number of ELFT service users in meaningful employment, education and training. | David Bridle Paul Binfield Angela Bartley | People Participation Team | Ongoing
5 | Increasing our understanding of population health and improved use of data systems to address inequalities | Use of Power BI platform with clinical teams to be able to see services by protected characteristics and deprivation Pilot of population health training session with primary care | Tom Nicholas Forid Alom Angela Bartley | Analytics Team QI Team | June 2021
6 | NHS England Tobacco Control Early Implementer Site learning and embed across ELFT | Workshops and learning sets (3 months) Pulling together in programme library (3 months) | Kate Corlett Angela Bartley Afia Khatun | Analytics & Performance team support on data collection People Participation | July 2021
7 | Develop Evaluation / metrics approach | Develop an evaluation framework for the workstreams across ELFT and measure success. Increase the number of academic publications from ELFT related to population health | Richard Fradgley Angela Bartley | Analytics Team R&D Team | September 2021
Public Health

## Slide 28
Access, Demand, Capacity
Digital First
Integrated Care, Partnerships & Coproduction
Staff & Service User Well-being
New Service Developments
Value
Workforce, Equality & Diversity
Estates
Bids & Contracts, Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
Communications
New Website/Intranet
Trust Rebrand
Bedford Health Village Engagement
Service User Accreditation
New Improved channels – e.g Youtibe, Interactive Trust Talks, ELFT Podcasts
Dedicated support for Digital First Strategy
Dedicated support for Primary Care
Strategic Objectives
Secondary Drivers
21-22 Priorities
Service User Outcomes

## Slide 29
No. | Top Key Priority Areas (Informatics) | Milestones | Local Leads | What Cooperate support is required | Expected Delivery Dates
1 | New Website/ Intranet |  | Steve Gladwin |  | Early 2022
2 | Trust Rebrand |  | Steve Gladwin |  | Summer 2022
3 | Dedicated support for Digital First Strategy |  | Steve Gladwin |  | June 2021
4 | Dedicated support for Primary Care |  | Steve Gladwin |  | April 2021
5 | Bedford Health Village Engagement |  | Steve Gladwin |  | On-going
6 | Communications Team seeking Service User Accreditation |  | Steve Gladwin | QA | TBC
7 | New and Improved Communication Channels e.g ELFT Youtube, interactive Trust Talk, ELFT Podcasts |  | Steve Gladwin |  | 12 months
Communications