## Slide 1: CHS Annual Plan 2022-23
March 2022

## Slide 2
Digital Offer
Staff Wellbeing, Recruitment and Retention
Service Developments
Integration and Co-Production
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Strategic Objectives
Secondary Drivers
22-23 Priorities
Establishment of discharge to access model of care
Demand and Capacity
Integration plan with Physical Health, Mental Health Services, Local Authority, Primary Care - Develop a dedicated plan to focus on joined up working rather than silo approach
Developing pathway modelling with system partners
Strengthen local partnership forums to align our priorities with GPs, PCNS, local authorities, acute trusts and system partners
Use digital offer to complete capacity and demand improvement plans – continue management through waiting times recovery plans
Listen to staff and match skillset with future service development – prioritise their interests
Alignment of training with needs of the organisation and staff
Consider financial incentives for staff recruitment
Introduce volunteers
Development of data, reports and performance dashboards in place to understand the pressures and impacts of initiatives
Improve IT skills and competencies – development of apps and telehealth
Ensure close monitoring of performance, use forecasting tools and learning from other services
Significant project demand – dedicated resource to support new projects
Service User Experience
Estates
Value
Link with local Higher Education Institutions
Digital inequalities -Review communication strategy with patients
Equality, Diversity and Inclusion

## Slide 3: Newham
Priority​ | Actions​ | Ownership​ | Challenges​ | Timelines​ | Support Required (internal)​ | Support required (external)​
Significant Project Demand​ | Recruit a joint post between CCG and ELFT (currently going through job evaluation)​ ​ | Helen Green & John Rooke​ People and Culture (job eval)​ | Keeping the day to day operations going while also implementing new projects​ Lack of capacity​ | 3 months​ | Recruit project support​ | ​
Waiting times reducing backlog​ | Recovery plans in place for all services​ Close monitoring of performance – learning from other services / teams​ Using platforms like AccuRX​ ​ | ​ | Plans are dependent on existing conditions – vulnerable to upsets e.g. another wave of covid, someone leaving etc.​ Tight for admin support​ | ​ | Programme support​ | ​
Recruitment and retention​ | Continue with use of dedicated resource​ Volunteers?​ Linking with local HEI ​ Changing contractual terms related to training (e.g. mandatory length of time to stay with the team after completion of training)​ Increased support for nurses and newly recruited band 5s​ OD to try to shift the culture surrounding new recruits / newly qualified staff​ Share HR data on staff turnover across the service – emphasise individual team leader responsibility for turnover​ Think about what financial support Newham can offer to make them stand out from the London weighting tension​ | People and Culture​ DMT​ | London weighting tension ​ People train with us but then leave to work in another team / service​ Lack of management support to new recruits because of lack of management capacity ​ Management culture of new recruits being seen as too much effort​ | ​ | Impact assessment for every new project that analyses the support and resource required to deliver​ ​ Programme support​ ​ People + Culture​ | ​

## Slide 4: Tower Hamlets
Priority​ | Actions​ | Ownership​ | Challenges​ | Timelines​ | Support Required (internal)​ | Support required (external)​
Staff wellbeing recovery and retention plan | Violence and aggression project recommences and produces action plan Spreadsheets in use are assessed against clinical system to minimise double entry of clinical information referrals from GP are of a high standard that reduce queries required by CHS teams Compassionate Leadership Principles and trauma informed management principles shared at DMT and service level meetings International recruitment for therapists commences Workforce plan outlining career Methodology developed to gather staff achievement and for this to be shared development in TH CHS | People and culture team | Lack of staff engagement Staffing levels | 31/05/2022 | TBC | TBC
Waiting Times and Reducing Backlog | Case load monitoring tool, case load review | Performance Team | Staffing levels | 31/12/2022 | TBC | ​TBC
Integrated Working | Working group established with Primary Care on improving effectiveness and quality Working group established with Royal London Hospital wards on improving effectiveness and quality Working group established with Royal London Hospital wards on improving effectiveness and quality | Alex Harborne/ Petra Nittel/ Alex Hadayah | Lack of engagement | 31/05/2022 | TBC | TBC