## Slide 1: Financial Viability Annual Plan 2022-23
March 2022

## Slide 2
Workforce, Equality and Diversity.
Integrated Care, Partnership Working and Coproduction
New Service Developments
Bids, Contracts & Commissioning
Value
Sustainability
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Strategic Objectives
Secondary Drivers
22-23 Priorities
Support and monitor delivery of clinical service transformation FV work stream e.g. older adult redesign, east London crisis, forensic outreach service etc.
Digital Improvements
Development of Single Point of Access in CAMHS and IAPT
Improve quality of north east London Mental Health Rehabilitation Placements
Forensics community outreach and low secure service design
Implement e-delivery option for service user letters and offer virtual appointments, meetings and training
Improve efficiency of records archiving process
Benefits realisation of community mental health transformation, process automation/digitisation to reduce paper processes
Improve quality / reduce cost of non-clinical contracts
Forensic Learning Disability Ward Expansion and partner with NELFT for the Assessment and Treatment Unit
Support & Monitor Delivery of new income generation (innovation) FV Workstream e.g. MSK screening, telehealth tools marketing, Digital support
Lead and monitor delivery of waste reduction FV Workstreams – e.g. carbon reduction/green plan, procurement, agency spend etc.
Reduced staff travel and increased agile working
Luton and Bedfordshire Mental Health rehabilitation service redesign, reduce Luton & Bedfordshire Section 117 spend
Develop a workshop model to monitor and follow-up methodology with outcome reporting in place.
Improve value strategic outcome performance indicators.
Value Culture Change work – implement a value organisational development plan and develop value section on ELFT intranet.

## Slide 3
Financial Viability Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External Support Required | Expected Delivery Dates + Timelines | Scale | Status
Value - Sustainability Link | Improved Value | Expand S&V Group to include service rep from all areas of Trust Expand S&V Group to include service user reps Value 'ambassadors' to join S&V Group Green Plan workstreams in place Ensure value incorporated into all workstreams Capture cost reduction related to sustainbility in FV Programme (see 8d) | FV PMO | Realising cost reduction: green initiatives often require investment. Rising energy prices may limit potential savings | Sustainability Leads + Green Plan Workstream Leads | Suppliers ICS Partners | 3-6 months | Trustwide | in progress
Value Improvement Workstream (QI/FV Collaboration) | Improved Value | Deliver waste tool training every 2 months Incorporate value improvement ideas into Value Improvement Workstream Incorporate value improvement ideas into Directorate plans Develop measurement/reporting structure | FV PMO | Sustaining improvement projects which truly reduce waste | Quality Improvement Team Directorate Management Teams | Institute for Health Improvement | 3 months | Trustwide | in progress
Value Culture Change Work | Improved Value | Waste Reduction Campaign Value/FV Intranet Page Value/FV Outward-facing Webpage Cost Reduction Tools & Data Regular Value/Waste Comms Use of Value/FV Branding | FV PMO FV Exec Leads | Communicating in a way which reaches all The ability to assign a cost to key processes | Comms Team Finance Team | Service Users / Key Partner support to develop outward-facing Value/FV webpage | 3 months | Trustwide | in progress
Trust-wide Benefits Framework | Improved Value | Develop benefit 'domains' built around Trust strategic outcomes Develop monitoring & reporting documentation Develop governance & reporting structure | FV PMO | Developing a process that is supportive & not onerous | Digital Team Trust-wide Stakeholders | Service Users (experience of care benefits) | 3 months | Trustwide | in progress
Improved Value Strategic Outcome Key Performance Indicators | Improved Value | Develop Improved Value KPIs Incorporate into FBIC bi-monthly reporting Incorporate into Trust Board quarterly reporting | FV PMO | Access to data | Performance Team Assurance Team | None | 3 months | Trustwide | in progress

## Slide 4
Financial Viability Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External Support Required | Expected Delivery Dates + Timelines | Scale | Status
Regional / ICS-wide FV Schemes with System Partners | Improved Value | Identify ICS partner efficiency leads Develop plan of joint FV schemes Agree split of savings across organisations Deliver plan of joint FV schemes | FV PMO | Understanding financial structure of systems | Finance Team Procurement Team Directorate Management Teams | System Partners | 6-12 months | Trustwide | Not started
Support & Monitor Delivery of Clinical Service Transformation FV Workstream | Improved Value | As per individual scheme | FV PMO |  |  |  |  |  | 
Older Adults Care Pathway Redesign | Improved Value | Identify capacity to undertake scoping Develop options business case Trust approval of preferred option Consult with partners on preferred option Implementation of preferred option | FV PMO + identified capacity to undertake scoping Exec Sponsor | Requires significant capacity to scope Will require engagement and support of local partners May get opposition from service users/ families/carers | Representation from 3 East London MH Directorates Representation from Communnity Health Directorate | Local Partners (Healthwatch etc) Commissioners Local Care Homes Service Users & Carers | 9-12 months Further phases will be delivered 23/24 | Local/Place-based | Not started
East London Crisis Line Redesign | Improved Value | Project team in place Develop clinical model and management structure Develop options business case Consult with partners on preferred option Implementation of preferred option | FVPMO Crisis Line Project Team Exec Sponsor | Potential opposition may delay implementation Directorate responsibility for an East London-wide service | Representation from 3 East London MH Directorates People & Culture Finance Digital Business Development Performance Estates | Local Partners Service Users & Carers Commissioners | 6-9 months | Local/Place-based | in progress
Forensic Community Outreach Service Redesign Phase 3 | Improved Value | Design clinical model and staffing structure Put Phase 3 team in place | FVPMO Forensic Directorate Management Team | Possible delay in receiving income | Business Development Finance | North East London Forensic Consortium | 3 months | Local/Place-based | in progress

## Slide 5
Financial Viability Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External Support Required | Expected Delivery Dates + Timelines | Scale | Status
Forensic High Intensity Ward Expansion | Improved Value | Agree expansion of ward by 1 bed with NEL Forensic Consortium Redesign clinical model and staffing structure Put enhanced ward team in place Transfer service user; additional income agreed | FVPMO Forensic Directorate Management Team | Balancing income with intensive staffing requirements, to ensure surplus | Business Development Finance | North East London Forensic Consortium | 3 months | Local/Place-based | Not started
Bedfordshire MH Rehab Redesign | Improved Value | Project team in place Develop tender documentation Run procurement process Contract awarded to successful applicant Staff restructure/TUPE process | FVPMO Senior management team: inpatient mental health (L&B) | Potential opposition may delay implementation | People & Culture Estates Finance | Commissioners VCSE organsations Local Partners | 3-6 months | Local/Place-based | in progress
NE London MH Rehab Redesign | Improved Value | Develop charging schedule for rehab support to other NHS Trusts Identify opportunities for residential placement cost reduction Run initiatives to realise cost reduction/improve value for money of placements | NEL MH Rehab Project Team | Engaging placement & commissioning partners | Finance Borough MH rehab clinical leads | Commissioners Local Partners | 3-12 months | Local/Place-based | in progress
Section 117 Spend reduction | Improved Value | Identify Exec sponsor Project team in place Identify opportunities for residential placement cost reduction Run initiatives to realise cost reduction/improve value for money of placements | L&B Section 117 Project Team | Engaging placement & commissioning partners | CMHT leads | Commisioners Local Partners | 12-24 months | Local/Place-based | in progress
Trust-wide Neurodevelopmental Pathway | Improved Value | Scope potential to deliver East London-wide Neuro Service (add Newham) Scope potential to include Luton & Bedfordshire | Trust-wide Mental Health Clinical Directors | Delivering a Trust-wide service with place-based elements | Finance Business Development Digital | Commissioners | 6-12 months | Trustwide | Not started
Community Health Services London Merge | Improved Value | Identify potential services where management structure and estates can be combined Identify Exec sponsor Project team in place Staff consultation process Implement change | TH & NH Community Health Leadership Team | Outcome of staff consultation could delay implementation | People & Culture Finance Estates Digital |  | 6-9 months | Local/Place-based | Not started

## Slide 6
Financial Viability Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External Support Required | Expected Delivery Dates + Timelines | Scale | Status
Lead & Monitor Delivery of Waste Redution FV Workstream | Improved Value |  |  |  |  |  |  |  | 
Procurement Cost Reduction Plan | Improved Value | Finalise 22/23 Plan Agree cash releasing process with Finance for each scheme Implement 22/23 Plan | Procurement | Having full procurement team in place | Finance | Suppliers ICS Partners | 3-12 months | Trustwide | in progress
E-delivery of Service User Correspondence | Improved Value | Test interface with supplier Run pilot with one service Analyse pilot; make any necessary changes Trust-wide roll-out | FVPMO Richmond IAPT (pilot) Trust-wide leads (full implementation phase) | Cybersecurity of email relay | Digital Team | Hybrid/EBO Supplier | 0-3 months (IAPT pilot) 3-12 months (Trust-wide) | Trustwide | in progress
Trust-wide Logistics Service | Improved Value | Exec approval to take Trust-wide approach Create JD Run 6-month pilot Analyse pilot | Director of Estates Heads of Admin Site Services Manager (City & Hackney) | Staff & Service User Safety Culture change | Estates Finance |  | 6-12 months | Trustwide | Not started
Carbon Reduction / Green Plan | Improved Value | Scope opportunities to reduce cost linked to carbon reduction | AD for Sustainability Sustainability Clinical Leads | Energy cost increases may limit savings Carbon reduction often requires investment up front | Sustainability & Value Steering Group S&V Workstream Teams Local Sustainability Leads | Suppliers | 6-12 months | Trustwide | in progress
Estates Optimisation | Improved Value | Identify buildings in scope Develop plan for each building in scope Implement plan for each building in scope | FVPMO Estates Directorate Leads | Ongoing social distancing may limit estates reduction potential Trust expansion Need for clinical space | Service leads | Local partners Landlords | 6-12 months | Trustwide | in progress

## Slide 7
Financial Viability Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External Support Required | Expected Delivery Dates + Timelines | Scale | Status
Corporate Process Redesign / Digitisation / Automation | Improved Value |  |  |  |  |  |  |  | 
Agency Spend | Improved Value | Project team in place Identify potential cost reduction opportunities | Agency Spend Project Team | Ongoing struggles with permanent recruitment Service safety if agency staff not in place to cover vacancies | People & Culture Trust-wide Service Leads Finance | Staffing agency suppliers | 6-12 months | Trustwide | in progress
Interpreting Service | Improved Value | Train service users to carry out interpretation for appointments Pilot & assess Identify potential to reduce external supplier spend through use of internal interpreters | Compass | Share savings with Compass | People Participation |  | 3-9 months | Trustwide | in progress
Support & Monitor Delivery of New Income Generation (Innovation) FV Workstream | Improved Value |  |  |  |  |  |  |  | 
IAPT Service Marketing | Improved Value | Identify further opportunities to contract with Irish Trusts | IAPT Senior Leadership Team |  | Finance Business Development | Partner organisations | 3-12 months | Trustwide | in progress
MSK Screening | Improved Value | Requires further scoping |  |  |  |  |  |  | 
People Participation Service | Improved Value | Requires further scoping |  |  |  |  |  |  | 
Peer Support Service | Improved Value | Requires further scoping |  |  |  |  |  |  | 
Mental Health Bed Sales | Improved Value | Requires further scoping |  |  |  |  |  |  | 
Dialog Support & Development Service | Improved Value | Requires further scoping |  |  |  |  |  |  | 
Telehealth Tools Marketing | Improved Value | Requires further scoping |  |  |  |  |  |  | 

## Slide 8
Financial Viability Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External Support Required | Expected Delivery Dates + Timelines | Scale | Status
Social Care Academy | Improved Value | Requires further scoping |  |  |  |  |  |  | 
Mental Health Care Homes | Improved Value | Requires further scoping |  |  |  |  |  |  | 
Monitor Delivery of New Income Generation (Overheads) FV Workstream | Improved Value | Identify total value of new investment Assign proportion to FV Programme Release savings on monthly basis | FVPMO Finance Business Development | Need to ensure this is a far less significant element of the FV Programme in 22/23 Balancing savings achieved through overheads and ensuring corporate functions have capacity to deal with clinical service expansions | Finance | Commissioners | 0-12 months | Trustwide | in progress