## Slide 1: Primary Care Annual Plan 2022-23
March 2021

## Slide 2
Service user outcomes
Staff Experience and Wellbeing
Integrated Care, Partnerships & Coproduction
New Service Developments
Sustainability
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Strategic Objectives
Secondary Drivers
22-23 Priorities
Tackling inequalities including the more hidden inequalities
Clinical outcomes
Further develop and share learning for homelessness work
Access: Demand and Capacity modelling
CQC Readiness
Working with system partners to develop ARRS roles
Training and development of the team – Primary Care Skills Academy (PCSA)
Workforce, people plan, recruitment and retention
Care Navigation
Implementation of the General Practice Support Unit (GPSU) – Beds only
Development of nursing team
People participation work – integrating into communities
National General Practice Access Improvement - Beds only
Performance review, WHO outcomes, COVID recovery, cancer detection, screening and immunisation
Comms strategy
Triple Aim Leighton Buzzard/Working Together Leighton Buzzard
Primary Care Podcast
Primary Care Network (PCN) prospectus
Delivering on Long Term Plans around Primary Care Networks
Financial Viability

## Slide 3
Priority | Explanation | What would good look like?
Improved Staff Experience | Training and development of the team – Primary Care Skills Academy (PCSA) | Continued staff development/progression/succession throughout Primary care directorate Prospectus of offers kept up to date Improved staff confidence and promote inclusive health strategy Capacity to support service users – patient proposed training in areas where there are gaps. Spread of expertise among clinical team (and potentially other practices) Implementation of a weekly/monthly user group Coding and improvement of recording on clinical systems
 | Workforce + People Plan + Recruitment + Retention | Engagement and upskilling through financing Training for patients in a supportive role Increase staff morale to reduce staff turnover, sickness and absence Flexible working Culture changes to improve working environment Growing leaders – becoming good role models and coaches Good supervision and delegation
 | Care Navigation | Directing people to the right services Improved experience Better integration e.g. housing Dashboard – helping to understand the gaps Improved triage system
Improving Population Health | Tackling inequalities including the more hidden inequalities | Patient advocates and training (developing a contract in Newham) – more work with groundswell Using learning from public health project and applying this to screening and patient engagement Developing PPG practices – what would they like to see improved? Have the patients drive this focus One Stop Shops – developing in-house resources Relationships with community e.g. improved housing services Access to physiotherapy and podiatry esp. in TH Share experiences across the practice
 | Further develop and share learning for homelessness work | 
Developing/Validating Priorities: East London

## Slide 4
Priority | Explanation | What would good look like?
Improved Staff Experience | Training and development of the team – Primary Care Skills Academy (PCSA) | Implementation of the PCSA across primary care support administrators and managers with key skills framework. All staff engaged in the offer, launched on LMS and having courses easily accessible, developing content for LMS. Staff feedback on the courses they experience and what they need to support development . Support progression in the Directorate , key skills framework
 | Implementation of the General Practice Support Unit (GPSU) | Centralisation of telephony in one place, administration and medication. Quick turnaround for key functions such as medication prescription Service user engagement in the deployment process Better understanding of population health/ needs of service users Establishing skills to support staff/ defining what we mean by population health- scope and define, and build on whats needed to support pop approach Improve patient feedback – qualitative Less complaints Good governance – datix reporting structure Power BI reporting and data easily available to understand and help staff to take appropriate action Staff agenda for change transition to be completed
 | Care Navigation | Launching in February - ensure front door processes can direct users to right resources Demand and capacity modelling, Training staff on what's available
 | Workforce + People Plan+ Recruitment and retention | Having right number of staff to cover roles, GP and admin staff in place Attract right person, quickly Ability to work flexibly and making roles attractive
 | Development of nursing team | Establish nursing leadership structure, having an extended scope for nursing staff to grow. Looking at different roles and functions, opportunities to have cross over roles (acute, PC and MH)
Developing/Validating Priorities: Luton & Beds

## Slide 5
Priority | Explanation | What would good look like?
Improved Clinical Outcomes | CQC Readiness | Good preparation of information around compliance, having good routine processes so its engrained in business as usual, systems are well oiled and part of everyday processes . Looking at areas were you are weak in terms of processes and systems so that they can be strengthened – practice level and service level plans, having information pack updated in evidence folder routinely
 | Working with system partners to develop ARRS roles | Having roles recruited into , all the resources available and utilisation of that resource around the PCN, defining the roles of the PCN and how they align with population health/inequalities and LA and public health agenda
 | Access: Demand and Capacity modelling | A clinical team that is designed to meet the needs of our population for appointment and contacts for each service - learn where the gaps are and filling the gaps – All services , particular Bedford services
Improved Experience of Care | People participation work – integrating into communities | Coproduced services with our PPL leads, not a tick box exercise Embedded into Directorate and having a mindset Linking to culture and leadership
Improved population health | Tacking inequalities including the more hidden inequalities | 6 strategic objectives – children and young people, service users and carers, employment and skills, reducing poverty, social justice, prevention of key groups
 | National General Practice Access Improvement | Caudwell practice – improving access, demand and capacity work to be completed to meet the needs of population
Developing/Validating Priorities: Luton & Beds (cont.)

## Slide 6
Priority | Actions | Ownership | Timelines | Challenges | Support required (internal) | Support required (external)
Training and Development of the team – PCSA | Identify the key skills areas and develop a KSF for East London, GPSU and A&C managers Review KSF to ascertain who will develop the course content Develop content Build a repository of materials Development of the key skills offer including details of how the skills academy bank account will work Develop a prospectus of offers and publish to staff Patient proposed training User group and develop activities Coding and recording on clinical systems Generate capacity. | Head of Skills Academy | Initial prospectus publication April 2022 |  | Practice managers OD People and Culture Clinicians LD Team | 
Care Navigation | Directing people to right services Improved experience Better integration e.g. housing Dashboard – understanding the gaps Improved triage system | Senior Leadership Teams (practice managers, deputy managers, GP leads and nursing leads) | 9 month review | Newly developed Having teams skills in care navigation Ensuring clear delivery Need to understand the significance of specific roles to signpost PCNs | Managed within the practice | Care navigation package
Workforce, people plan, recruitment and retention | Engagement and upskilling through financing Training for patients in a supporting role Highly skilled workforce and reduction in staff turnover, sickness and absence Flexible working Work culture and uplifting morale Empowerment Growing leaders and role modelling – coaching and mentoring Supervision | Senior Leadership teams (clinical and non-clinical) People and Culture Joint ownership – all staff Committee ownership Finance | Ongoing People Plan (overhanging document – TBC) | Different between responsibility and accountability Overspend Broader team by-in Supporting structures need to be tailored to Primary Care | Service lead monthly meetings People and culture LD Team | CCG support and funding
People Participation work – integrating into communities | Establishing PPG Getting the PPG to set goals and make it patient driven Talk to the practice – what do the patients want to prioritise? Engaging a wider group of service users | PPG |  | Making patient participation meaningful and gaining a wide range of engagement Establishing aims and vision – avoid making this transactional with service users |  | 
Primary Care Annual Plan Priorities 22-23 East London

## Slide 7
Priority | Actions | Ownership | Timelines | Challenges | Support required (internal) | Support required (external)
Tackling inequalities/Further develop and share learning for homelessness work | Patient advocates – training programme patients need to help other patients Learning from public health project inequality project Developing PPG in practices One stop shop Developing relationships with community Commission Groundswell like Greenhouse in HE1 Shared experiences Access to podiatry and psychotherapy. | Senior leadership teams, PPG lead within the practice, Emily (Public Health) | 12 months + (ongoing) | HE1 and Greenhouse – room challenges – build partnership with CIC to have the One Stop Shop Funding Asylum seeking population – hotels, mental health etc. Breaking down barriers with service users – developing trust | Population health Team PPG MDT integrated work e.g. homeless partnership team | Groundswell PCNs Greenhouse Multi Agency Partnership (CH) – start partnership across NH and TH CCGs
Primary Care Annual Plan Priorities 22-23 East London

## Slide 8
Priority | Actions | Ownership | Timelines | Challenges | Support required (internal) | Support required (external)
Training and Development of the team – Primary Care Skills Academy (PCSA) | Develop content Build a repository of materials Development of the key skills offer including details of how the skills academy bank account will work Rollout a prospectus of offers and publish to staff Identification of key groups of staff that need development support – targeted approach to delivery Virtual training offer at home – reports in place to monitor engagement via LMS Training and development for opportunities to grow – skills and experiences | Head of Skills Academy Primary Skills Academy Board | Initial prospectus publication May 2022 | Giving staff the time for personal development, capacity | Practice Managers People and culture Clinicians LD team | OD , Acute and other providers to support career opportunities , PCN colleagues
Implementation of the General Practice Support Unit (GPSU) – Beds only | Implement new telephone system – confirm date across Bedfordshire Project timeline Report and data available to understand how services are performing Strategic work to understand scope of population health agenda and training staff Teams and management structure in place OD work with staff plan in place Protocol and processes embedded and deployed to support new system Learning from the implementation – whats working better and whats not Benefits realisation | PMO | April – kick off 6-12 month – mobilisation 2 year to embed to fully | Successful outsourcing in the PMO function –no capacity at the moment Recruitment of the clinical and operational leads | External PMO in place , Practice Managers, Clinical Leads | Support from CCG around telephony and IT, P&C, OD, Estates, Communication, Finance
Workforce + People Plan + Recruitment and retention | Identify initiatives to attract people to roles i.e. benefits for staff, flexible working QI project – to look at recruitment for P&C Working with resourcing team Having right number of staff to cover roles, GP and admin staff in place Attract right person, quickly Ability to work flexibly and making roles attractive |  |  |  |  | 
Primary Care Annual Plan Priorities 22-23 Luton & Beds

## Slide 9
Priority | Actions | Ownership | Timelines | Challenges | Support required (internal) | Support required (external)
Tackling inequalities including the more hidden inequalities | Each practice to identify a specific population to work with Articulate an ambition and plan around the 6 objectives – plan phase to be completed (what its doing now and how it can design future work) Workshop to define the scope further Working with Primary Care Foundation to identify population health target groups that need support and focus Cervical Screening and other existing work to build on tackling inequalities Data/ reporting in place - Identification of consistent way of searching data and population | DMT with support from Public Health | 12 months | xisting pressures on team, lack of staff and thinking space for additional work – keeping the lights on is priority , capacity , service user engagement in workstreams | Administrators and data support to have high quality data | Public Health team, Primary Care Foundation , IT , Communication
Primary Care Annual Plan Priorities 22-23 Luton & Beds