## Slide 1: SCYPS Annual Plan 2022-23

## Slide 2
Service Development
Digital Strategy
Estates
SCYPS MDT working
Service user involvement, engagement and partnership
Transformation and mulit-agency service delivery
Multi-Professional Research
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Building pathways with 0-19 services
Workforce Development
Engage in Marmot Trust Values
Recruit PPL(s)
PP engagement on SEND Board/QI Forum/Away day
MDT Triage process
MDT Working Group to improve pathway working
Improve clinic space ensure fit for purpose
Full utilisation of space
Sckle cell commissioning and CCNS, SLT Integration, physiotherapy
CCNS – Extended hour (Funding dependant)
Review of provision/funding - Physio/SC&T
Strategy to recruit with new investment
RiO Transformation
Formalise data recording and processes (DQ)
Continue building research project across disciplines
Create additional capacity I.e project manage, parent trainers

## Slide 3
Priority​ | Actions​ | Ownership​ | Timelines​ | Challenges​ | Support required (internal)​ | Support required (external)​
Estates – improving clinic space and rooms being fit for purpose​ | QI Project​ Engagement with plan to develop Morrison site​ Co-location​ Community hub ​ Creating vision with existing staff – user involvement ​ Hotdesking system​ | Sarah Skeels​ | Within 1 year (QI project)​ 4-5 years (Morrison site)​ | NHSPS contracts​ Capacity and resources​ Cost​ Extended hours – weekend working​ Buy-in​ | Project manager post​ ​ | QI training and corporate support​ Estates​ IT​ Financial viability​
Service user involvement, engagement and partnership​ | Recruitment B5​ Recruit lived experience​ Family ambassadors​ Engagement with all services – embedding vision of service user partnership.​ Culture change – harnessing service user perspectives​ Partnership working – working with already established links​ Away Day​ | SMG​ ​ | 6 months ​ | Time ​ Cultural resistance – link to EDI work​ Conflicts with other forums​ Duplication ​ Recruitment to B5 post​ | Team leads buy in​ | Paul Binfield ​ Comms ​ Admin​
Workforce development – implement SEND actions​ | Increasing project management capacity​ Employing parent trainers – co-facilitated training and workshops​ Parent representative on SEND board​ Rethink offer – innovation and creative solutions​ Away Day – think about USP and develop workstreams​ Review JDs and marketing strategy​ International recruitment – understanding offer​ Escalation process with HR​ Rotational schemes​ SCYPS apprenticeship programme​ | Profession leads​ SMG - oversight​ | 6 months​ | Corporate leads link​ Nursing​ | ​ | Finance ​ HR – representatives at SMG​ Corporate connections​

## Slide 4
Priority​ | Actions​ | Ownership​ | Timelines​ | Challenges​ | Support required (internal)​ | Support required (external)​
SCYPS MDT working (triage, pathways, communication) | Plans are being further developed in the DMT | TBC | TBC | TBC | TBC | TBC
Digital strategy and improving data quality | Plans are being further developed in the DMT | TBC | TBC | TBC | TBC | TBC
Service development - sickle cell commissioning and CCNS, SLT Integration, physiotherapy | Plans are being further developed in the DMT | TBC | TBC | TBC | TBC | TBC
Transformation and multi-agency delivery of services | Plans are being further developed in the DMT | TBC | TBC | TBC | TBC | TBC
Multi-professional research | Plans are being further developed in the DMT | TBC | TBC | TBC | TBC | TBC