## Slide 1: People with substance misuse problems
4.1 Progress against the 2022-23 Trust-wide annual plan - 14 programmes of work
Improved Population Health Outcomes
Delivery of Recruitment and Retention Strategy Group action plan
Improved Value
Financial Viability programme
Implementation of the Trust’s Green Plan
Improved Staff Experience
Reducing waiting lists and backlogs
CAMHS Tier 4 bed capacity and flow project
Improved Experience of Care
Mental health crisis pathway\redesign
CMHT transformation
Strengthen safety culture and systems, including the new national Patient Safety Incident Response Framework
Initiation of a reuse scheme & increasing the Trust recycling provision to 70%
Implementation of a centralised temporary staffing function
Implementation of a WiFi programme and Cloud Hosting
More employment opportunities for people with lived experience
Implementation of the General Practice Support Unit (GPSU)
Developing ELFT as a Marmot Trust and implementing the Marmot principles

## Slide 2
Priority: Mental health crisis pathway redesign | Contact: Andrew Horobin, Deputy Borough Director - City and Hackney
Milestones
Aiming to move into the Raybould Centre on the 17th April
Formal consultation has been completed
Officially starting to use C-Talk from 17th April
Status: partially-completed
Progress and learning over Quarter 4
A project is being set up to renovate the Raybould Centre as the new crisis assessment suite and is nearly completed, awaiting furniture and desks for staff. It is hoped that this will be completed mid-April Official start date to use C-Talk scheduled for 17th of April with training currently being finalised with the team A staff consultation has been held to reformat work, including the new team starting on the 17th of April with a new rota in place Vacant positions have been recruited to Regular meetings are being held with community teams to clarify roles within the pathways for service users. Once the teams move into the correct teams, the team will priorities the operational and clinical changes that require implementation
Next Steps…
Plans to embed the new model of working and testing out theories around service provision - testing is currently underway for delivery In June, plans are in place to restart the Triage model and move service users out of the emergency department into the Raybould department for a full assessment A psychiatric liaison review is underway across the North-East London (NEL) footprint which will impact staff and how we are providing our service, meaning that the team may have to adapt to any proposals
Improved population health outcomes
Challenges and what we have learned
Main challenges have been around moving from one contract to another which has instigated delays to transition to the new telephony system Delays occurring around the Raybould renovation particularly around resourcing estates to ensure optimal service function that meets the needs of stakeholders Strategic challenges include aligning this project to other Trustwide priorities and competing with shifting priorities for the centralised crisis line have impacted local crisis pathway provision Main lessons learned have been around the importance of staff engagement in the changes to the processes, supported by the importance of maintaining an adaptable and flexible approach to shifting priorities

## Slide 3
Priority: CMHT Transformation | Contact: Jamie Stafford, Programme Director CHMT Programme
Milestones
Progression of the Let's Talk Report in each borough alongside collaboration with the inequalities team
Increasing use of Dialog across the Trust
Introduction of new roles including Community Connectors, ARRS Mental Health Practitioners, GP Mental Health Leads, and Peer Support Workers
Adults on the SMI register receiving physical health checks
Status: in progress, continuing in 2023/24
Progress and learning over Quarter 4
Currently initiating the design phase of the replacement framework for CPA Expansion of our Patients Know Best pilot to include the Early Intervention in Psychosis teams in East London Stocktake activity has been completed to determine our current position against the national expectations for the Long-Term Plan period to ensure activities are on track System Development Funding (SDF) planning for new 2024 allocations is required and discussions are due to be carried out in each of the boroughs to understand their specific plans Various workstreams around Care Act assessments, Dialog and Dialog+ have been brought together to ensure consistency across all domains
Next Steps…
Changing waiting times standards are underway for the next quarter to understand changes to reporting Development of plans to focus on increasing cultural safety due to increasing collaboration with the inequalities team CPA Expansion to move from the design phase into implementation regarding Triage forms, Care Plans, and Dialog+ and bring standardisation into practice Official transition to "business as usual" process and working towards a programme plan for 2023/24 based on a "business as usual" footing
Improved population health outcomes
Challenges and what we have learned
Moving towards the "business as usual" approach has been a challenge to understand how best to build capacity to maintain the progress of ongoing work and recognising the integrated nature of new services Conflicting priorities and wider system changes in Primary Care and with the ICB have posed challenges to maintaining staff engagement and requires learning to understand how to further integrate services in times of change

## Slide 4
Priority: Developing ELFT as a Marmot Trust and implementing the Marmot principles | Contact: Angela Bartley, Deputy Director of Population Health
Milestones
Developed learning materials for IHE and UCLP learning networks
Partnership with HSBC and East London Business Alliance on financial support and health literacy
Status: in progress, continuing in 2023/24
Progress and learning over Quarter 4
ELFT Case Study is being used to launch the IHE NHS Marmot network and contributing to UCLP good practice for NHS Trusts playbook Ethics research proposal for SCYPS and healthier wealthier families has been approved by UCL ELFT have signed up as a charity partner to HSBCs financial services scheme to increase access to bank accounts. Staff from ELFT homeless team have been trained by HSBC on setting up bank accounts QI inclusive recruitment with Borough of Luton is now ongoing and we have started to recruit local community members to ELFT jobs. Extending this offer to admin and HCA roles SCYPS Newham have started the Healthy Wealthier programme in February with UCL and are developing family literacy offer with CAMHS and the East London Business Alliance (ELBA)
Next Steps…
Plans underway to talking to the Irish National Health Service about the Marmot work at ELFT Plans to continue sharing learning and evaluating progress with other NHS Trusts, IHE and UCLP Continue to strengthen the Inclusive recruitment programme in Luton Healthy Wealthier Programme and Literacy programme to continue for the next 9 months
Improved population health outcomes
Challenges and what we have learned
Balance between a place-based approach and corporate objectives has caused challenges around conflicting priorities Transferring Marmot projects to a business-as-usual approach has been a challenge

## Slide 5
Priority: Implementation of the General Practice Support Unit (GPSU) | Contact: Lizzy Burraway, GPSU Manager
Milestones
13 Standard Operating Procedures (SOPs) have been signed off by the QAG, meaning there are no SOPs remaining
"Go live" of the GPSU for the 8th of June
Status: Completed
Progress and learning over Quarter 4
Process is now in place where staff can scan Coordinate My Care (CMC) repeat prescription requests which is being led by the GPSU New registrations for CMC prescriptions are now in place A "soft" launch of the GPSU has been rolled out and teams have gone live, however, the official go-live is scheduled for June People Participation Group (PPG) members continue to be involved with the sign-off process of the GPSU, ensuring service user co-production in the process Organisational Development (OD) sessions have taken place, with Team Leads and Senior Primary Care Management teams undergoing a second session The Community Pharmacist Consultation Service (CPCS) was put on hold, but has now recommenced Care Navigation training has taken place for internal services, with a site visit due to provide further feedback
Next Steps…
“Go live" date for the GPSU on the 8th of June Lots of work is underway to review abandoned missed calls which are currently disrupting telephone figures. The highest frequent callers have been identified and contacted to understand the reasons for abandoning calls Plans are in place to work with the Communications Team to abandoned calls from the call figures to avoid confusion KPIs to be addressed within SOPs to ensure regular oversight Auto-reminders on systems for pre-bookable appointments are being explored to reduce DNAs
Improved experience of care
Challenges and what we have learned
Current struggle is around answering calls within the 10-minute target, teams are operating from 8am to 6:30pm ensuring someone is always on hand Access to compliance reports is limited to monitor performance on meeting the 10-minute target. This has currently been escalated to the local performance leads for oversight Retention has been a challenge, however ongoing recruitment efforts have been successful and there are currently 2 positions still vacant (1 wte patient coordinator and 1 wte population health lead)

## Slide 6
Priority: CAMHS Tier 4 bed capacity and flow project | Contact: Lawrence Chung, Transformation Project Manager
Milestones
Opening of the Evergreen Unit
Successful recruitment to main vacancies
Currently accepting patients with 2 patients discharged
Status: Completed
Progress and learning over Quarter 4
Evergreen is now open and will be accepting admissions from 20th April, initially accepting patients from BLMK, with admissions being managed by the East of England patient flow team Most key posts have been recruited to and the only vacancy remaining is a Band 7 OT, with a drive to over-recruit Bands 3-6. The team are reviewing all referrals to the Bed Management Team and staggering admissions to manage flow Education provision in place and is being funded by Local Authority partners The team have established a routine around key meetings, Senior Management Team (SMT) and Object Management Group (OMG) have reviewed the remit of these meetings to ensure they are fit-for-purpose Preparation for stakeholder engagement, public engagement and communications have been planned leading up to the opening of Evergreen
Next Steps…
Quality Improvement workstream to be established and led by Associate Clinical Director to optimise admissions Plans to launch equalities work in Evergreen Regular review planning to be held with the team to think about the current environment and how it is functioning Focus on staff wellbeing and setting up systems and governance to enable seamless working including a formal induction process, and booking QNIC (Quality Network for Inpatient CAMHS) in the process of being set up
Improved experience of care
Challenges and what we learned from them
Challenges have been around the environment, specifically around limited space and thinking creatively about using other spaces on the wards to increase this Challenges exist around recruiting experienced staff as current team is relatively young and opportunities are being scoped to upskill the workforce Focus on staff retention and keeping staff motivated and engaged while working in challenging environments. Support plans and projects implemented concurrently with recruitment drive Ensuring the integrity of the model and being specific around referral management and can cause challenges with wider partners and stakeholders

## Slide 7
Priority: Reducing waiting lists and backlogs | Contact: Amrus Ali, Associate Director of Performance
Milestones
Progress towards reducing waiting lists and backlogs for all services, particularly the 11 priority areas
Recovery plans regularly updated monthly and/or regular forums have been established where regular progress updates are provided
Status: in progress, continuing in 2023/24
Progress and learning over Quarter 4
11 high-priority services across the Trust have been identified to focus efforts on and we have supported teams to set up regular performance meetings where demand and capacity are routinely monitored Successful change ideas have been implemented across the Trust. Many of these include redesigning patient pathways to identify which roles and responsibilities can be shared to increase clinical capacity. Several services have successfully trialled group therapy sessions to support multiple service users simultaneously Based on rigorous demand and capacity analysis across the Luton & Bedfordshire Autism team, the backlog recovery plan has been adapted to make it easier for teams to map demand and capacity visually across the pathway to understand potential bottlenecks and identify change ideas to backfill certain positions
Next Steps…
A review of the new waiting times standard is underway to see how this will influence reporting of waiting times. Regular oversight forums will be held to ensure that teams are aware of the changes and what this means for their data Ensuring that the 11 high priority services are regularly updating the recovery plan to ensure that the robust mechanisms that are in place are maintained. Dedicated performance sessions to be held in May with Community Health Services providing additional coaching on demand and capacity and applying improvement tools.
Improved experience of care
Challenges and what we learned from them
Access to accurate and timely data to review waiting times and iron out data inconsistencies with the informatics team Working closely with local performance and clinical leads has been essential to ensuring that regular updates on the recovery plans are provided and having regular interface meetings to streamline assurance and understand the current situation Teams have been struggling with capacity due to ongoing recruitment challenges, therefore we have been working with teams to think about innovate ways of expanding capacity with the resources that we have to increase workforce productivity

## Slide 8
Priority: Strengthen safety culture and systems, including the new national Patient Safety Incident Response Framework (PSIRF) | Contact: Deborah Dover, Director of Patient Safety
Milestones
Preparation for implementation of the Learning from Patient Safety Events (LFPSE) in September 2023
Preparation for PSIRF transition in October 2023
Patient Safety Partners in post
Completion of Year 1 PSIRF training by September 2023
Draft PSIRF plan and policy to be drafted by 30th June 2023
Status: in progress, continuing in 2023/24
Progress and learning over Quarter 4
Draft patient safety plan has been co-produced, presented and accepted by the board. - Staff and stakeholder engagement work has taken place and measures to evaluate progress are being defined. PSIRF - training has commenced and new learning methods are being piloted. PSIRF lead appointed and an open forum to engage staff, service users and system partners has commenced. PSIRF implementation steering group continues to lead work toward PSIRF plan, policy and transition. Patient safety syllabus modules established on ELFT’s learning academy Patient safety learning quality improvement initiative commenced, and safety learning and improvement event has taken place Trustwide Safety culture inpatient team self-assessment tool has been piloted and is in further development Recruitment to patient safety partners has commenced
Next Steps…
PSIRF – Year 1 training to be completed and continued progress towards transition via implementation plan anticipated Commencement of patient safety partners in role. Work to transition to the new incident reporting system to continue Work towards collaboration with NIHR Safety Culture Research Group to continue Triggering of Safety II learning initiatives planned for Quarter 1 2023/24
Improved experience of care
Challenges and what we have learned
Challenges relating to transition from existing incident framework to new PSIRF Resources remains to be a challenge for this work Complexity of achieving changes of patient safety culture Nationally mandated changes to our incident reporting framework (LFPSE) may impact on reporting levels and culture

## Slide 9
Priority: More employment opportunities for people with lived experience | Contact: Angela Bartley, Deputy Director of Population Health
Milestones
Setting board level reporting data on employment for service users
Increased recruitment through the Luton inclusive employment QI project
Development of the 2-year Anchor Plan
Status: in progress, continuing in 2023/24
Progress and learning over Quarter 4
Continued focus on inclusive employment and development of ambitions for ELFT as an organization Learning from across ELFT on place-based schemes that are recruiting people into posts – Luton and Newham in particular QI project on inclusive recruitment in Luton with Luton Borough Council’s employability programme – people have started to be recruited to ELFT from this project. Developing straight to interview approaches for care leavers and people with SMI Dissemination of survey on employment with clinicians
Next Steps…
Conducting focus groups with clinicians to identify barriers to increasing employment with service users Dashboard development on employment is underway Draft Anchor plan on employment ambitions 2023/25 has been developed and is currently being reviewed
Improved experience of care
Challenges and what we have learned from them
Developing routine data collection on employment figures from a range of IPS and other services The employment steering group has 20+ regular service users on it which has really helped shape the work of the group and what they focus on Clinical time to help shape this work has been a challenge despite there being an increased focus on employment as a key recovery outcome.

## Slide 10
Priority: Delivery of recruitment and retention strategy group action plan | Contact: Sonia Kaur, Head of Resourcing
Milestones
Time to hire currently at 37 days which is below the 43 days KPI and has been sustained throughout the year
Downward trend of vacancy rate continues currently at 8%, despite a 6.84% increase in establishment
Direct overseas recruitment in medical and allied health categories of 80 WTE in the last 12 months
BAF financial authorisation process now moved to Track authorisation which was completed in March 2023
Status: in progress, continuing in 2023/24
Progress and learning over Quarter 4
In Quarter 4, 31 new apprentices were recruited, 19 of which were Clinical Associate Psychologist (CAP) apprentices. This means that the CAP apprentice total is 50. This is due to exploring additional routes to recruitment by utilising the apprenticeship levy in a more sustained manner Further progress made around international recruitment of capital nurses via capital programme, direct overseas recruitment and partnership working across ICBs. Workforce planning resulted in a change to process and highlighted gaps in nursing recruitment. The Executive Team have given approval to "over-recruit" into nursing with further hotspots identified in Luton and Bedfordshire New ways of working identified to impact medical recruitment across Luton & Bedfordshire and CAMHS
Next Steps…
Have identified direct overseas recruitment route from partners in Sri Lanka for nursing and other staff groups Stronger focus on recruiting overseas nurses via direct applications made on our recruitment portal New ways of working identified to impact medical recruitment across Luton & Bedfordshire and CAMHS Partnership working across BLMK and East of England (EoE) to recruit jointly and looking to do a recruitment campaign in the next 6 months for CAMHS Direct working with schools and education establishments to improve the work experience offer including Langdon Park School, Leyton College and Barking & Dagenham College
Improved staff experience
Challenges and what we have learned from them:
Lack of a trained workforce pool continues to remain a challenge in the market, currently looking at more entry level roles and role redesign processes through positive outcomes via initiatives for international recruitment in different staffing groups Prior difficulty with recruiting managed however, greater engagement efforts have shaped the way in which we recruit in a positive manner Blockages in the pipeline continue to be resolved with increased engagement with hiring managers

## Slide 11
Priority: Implementation of centralised temporary staffing function | Contact: Sonia Kaur, Head of Resourcing
Milestones
Reduction on agency spend in hot spot areas by recruiting into vacant roles
Onboard additional Framework agencies and better system in place to screen and onboard agencies in partnership with procurement
Agency to bank conversion of medics
Inactive Bank staff termination date extended from 6 to 12 months to aid bank retention
Status: in progress
Progress and learning over Quarter 4
Centralised Bank recruitment for Admin and Clinical roles of all staffing groups except Medical to temporary staffing (medical Bank recruitment via Medical recruitment team process streamlined). Bank recruitment events ongoing for London and Luton & Bedfordshire HCSW, B5 nursing and admin roles Specialised Bank adverts for services to develop their own pool of Bank staff for all professional groups including non-clinical helping spend less on Agency is ongoing Agency staff being inputted centrally on HealthRoster to record agency use with the objective of reporting on the usage (for Non-Medical /Non AHP). This objective is linked to the temporary staffing development group Temporary staffing developing group relaunched focusing around 6 workstreams: Bank Rates Review, Collaborative Bank, Changing Direct Engagement Provider, Temporary Staffing Model, Agency Spend Reduction and Project Governance
Next Steps…
"24/7 Direct Engagement Model" approved and now in implementation phase Bank rates review being conducted to produce streamlined and revised rates across all staffing groups Reducing Non-Framework agency usage remains a continued focus Provide training and continually engage with managers on temporary staffing processes and systems is ongoing via pipeline meetings Revise and review SOPs and KPIs for bank and agency Agency reduction across medical nursing and admin usage is to be continued Develop a PSL in partnership with Procurement to drive competition
Improved experience of care
Challenges and what we have learned from them:
Buy in from managers Trust wide to comply with the revised processes to enable Centralisation of Temporary Staffing Booking Improved Adherence to Framework rules and rates National shortage of trained staff to fill substantive roles leading to a reliance on long term bank and agency use to cover hard to fill roles To continue educating managers to use bank as an immediate means to fill their shift and agency as a last resort To continue utilising Healthroster optimally to enable maximum shifts to be filled and reduce the impact of unfilled shifts

## Slide 12
Priority: Financial Viability (FV) programme | Contact: Sarah Barnett, Financial Viability Programme Manager
Status: Half of 2022/23 target met, planning work for 2023/24 programme
Progress and learning over Quarter 4
Non-recurrent measures have increasingly been utilised to support the Trust to achieve a balanced financial position at year-end FV PMO has supported all directorates to develop more robust plans for 2023/24 January and February focused on regular performance meetings with operational directorates on financial viability in Q4 Service Delivery Board provided challenge and support for with Trustwide Financial Viability delivery A final plan was submitted to NHSEI at the end of Q4 with a £4 million gap in plans (against a £20.8 million 2023/24 target) Financial Viability was a more explicit part of Trustwide annual planning for 2023/24
Next Steps…
Planning work underway to meet the £20.8 million Financial Viability savings target for 2023/24 Monthly FV monitoring meetings will commence from April 2023 Financial viability targets will be devolved to all directorates from April 2023 to improve the visibility of the requirements Considering additional capacity required to support operational directorates to achieve an increased financial viability savings target
Improved value
Milestones
Actual year-end delivery is £7.24 million against the £15 million savings target
33% of the £15 million target has been delivered through recurrent schemes
Challenges and what we have learned
Identifying sufficient recurrent schemes has been a challenge during 2022/23, working with operational directorates to identify clinical transformation schemes is a priority Opportunities to utilise new income to support FV delivery are much reduced, working to identify cash releasing waste reduction, sustainability and transformation schemes

## Slide 13
Priority: Implementation of the Trust’s Green Plan | Contact: Adam Toll, Assistant Director of Estates
Milestones
After a 17% reduction in overall energy use for 21/22, a further reduction for 22/23 of 5% is planned
Streamlining work streams to ensure as an effective Green Plan as possible is in place
Status: in progress, continuing in 2023/24
Progress and learning over Quarter 4
6 work streams are now fully operational and being managed monthly through Work to update the Green Plan for 23/24 is almost complete and will be signed off this month at FBIC Service user involvement greatly increased in the last quarter and now embedded in to the work streams Significant progress and planning has been made, and the targets and goals within each work stream are being commenced and completed. Since the inception of the Green Plan, we are now showing on average a 61% completion rate within the 1st year of the plan. As the work to further imbed sustainability in to annual plans continues we have managed to include a sustainability related award in the annual staff awards ceremony We continue to develop our dashboard in line with Greener NHS and online green plan assessment tool that has recently been released. We hope that this will now be fully ready for Q2 or 23/24
Next Steps…
A fully functioning dashboard will be created for Q2 of 23/24 to help track measurable and provide assurance to all that the Green Plan and its associated actions and targets are having an impact on our carbon footprint Attendance at multiple departmental and Trust wide events to talk on sustainability and embedding the Green Plan in to the Trust planned.
Improved value
Challenges and what we have learned
With a number of separate reporting mechanisms within the Trust it is essential that we ensure not only consistency but lack of duplication We are working to ensure that ELFT internal assurance reporting methodology is as closely linked to the current Greener NHS carbon reporting as possible. Obtaining the formulas and calculations for energy and overall carbon footprint is ongoing.

## Slide 14
Priority: AWS Cloud Hosting and WiFi Programme Implementation | Contact: Sajini Nedumaran, senior digital infrastructure & service improvement programme manager
Status: Completed
Progress and learning over Quarter 4
Secondary DirectConnect2 (DC2) link between Alie Street and AWS has been created Discussions have begun with Telefonica Tech (TT) and Virgin Media for business is taking place with regards to ensuring cloud supplier resilience Kickstarting the remaining on-premises system migration project Started on the configuration of the wireless LAN controllers – configuration at The Green completed and access points at The Green migrated onto the wireless LAN controllers Adequate testing completed successfully
Next Steps…
Working on improving DC2 resilience, implementation details are yet to be confirmed The topology and architecture of a Trustwide overarching site resilience solution including cloud access are being defined (SD-WAN) Configuration of the wireless LAN controllers at both Alie Street and Charter House to be completed with testing in April – May 2023 Migration of all APs at both Alie Street and Charter House onto the wireless LAN controllers between April and May 2023 Migration of APs on the current Green/Alie Street/Charter House controllers onto the new Green/Alie Street/Charter House controllers in May – June 2023 Refresh of APs to be undertaken across the Trust for June – September 2023
Improved value
Milestones
Cloud access resilience completion
On-premises system reminders to be migrated to the cloud
Complete configuration of the wireless LAN controllers
Challenges and what we have learned from them
Interaction with other key programmes requires close attention with regards to key resources, dependencies and time management Go-live arrangements are best planned with backup dates Bottlenecks in internal and external key resources can create disruptive delays on the critical path. Widening internal teams' and suppliers' engagement does help Efficiently injecting the reality of true urgency shortens lead times Critical projects tend to impact on other projects' delivery, but some tasks can be combined across a portfolio to ensure delivery continuity

## Slide 15
Priority: Initiation of a reuse scheme & increasing the Trust recycling provision to 70% | Contact: Adam Toll, Assistant Director of Estates
Milestones
Currently have 82% coverage of recycling facilities. A 2% increase from previous quarter
The current figure of actual recycling volumes is 56%. A 4% increase from previous quarter.
Status: Completed
Progress and learning over Quarter 4
The Reyooz organisation and the work they are doing has now been utilised across multiple sites to great effect. The John Howard Centre has now been included in the scheme Work required to facilitate the efficacy of the project is underway at certain inpatient sites in a bid to improve the quality of materials being used. For example, ensuring items are kept dry and the teams are aware of the process for collection Continued waste audits, changing signage and improving facilities and discussions with staff are clearly showing benefits as recycling rates continue to climb
Next Steps…
The programme will now be rolled out at larger inpatient sites and ad-hoc as required at community sites The next planned site is Twinwoods and then Calnwood Court in Luton and Bedfordshire. This has not been completed from last quarter so the task will be rolled over. A planned 85% coverage to be achieved by next quarter. Same as previous quarter. Also looking at how we maximise the actual recycling volume from the current figure of 56%
Improved value
Challenges and what we have learned from them
Unless staff and contractors are fully committed and signed up to the reuse scheme and recycling, then the system will not succeed. Involving sub-contractors like the OCS and Rydons in meetings has been beneficial in relaying this message The ongoing challenge of ensuring staff is using the correct receptacles remains. Awareness, site visits, and communications are key to continue driving home the message that we must recycle where possible.