## Slide 1
Information Governance
2024/25 Annual Plan Priorities
Improved Population Health
Improved Experience of Care
Improved Staff Experience
Improved Value
Trust Strategic Objective
Priority areas for the service
DSPT Compliance
Asset register improvement project
Ensure full compliance of the Data and Security Protection Toolkit (DSPT) by the end of Quarter 1 to ensure cost saving by achieving early compliance
Ensure 100% compliance
Information governance locality audits to be up to date by Quarter 2 and determine which assets are no longer required to meet financial viability goals
Defined workstreams / projects / programmes for 24-25
SAR Compliance
Ensure that 0% are not overdue by Quarter 2 by ensuring that Subject Access Requests (SARs) do not go over the 30 days or beyond extension
SAR Templates and Internal Processes
Update templates to ensure that these are fit for purpose and create and send internal processes, to ensure efficiency of individuals answering SAR requests
SARs Team Development
Identify training and development needs to discuss this further at staff appraisals
Launch training and development programme by Quarter 2

## Slide 2
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | How does this link to your FV and Sustainability goals? | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  |  | 
DSPT Compliance | Full completion | Business as usual | Business as usual | Business as usual | No further recommendations | Save cost by achieving early compliance | Cooperation from services in the Trust | Keshia Harvey
Asset Register Improvement Project | 80% compliant | 100% compliant | Business as usual | Business as usual | IG locality audits identify up to date audits | Determine which assets are no longer required (FV) | Cooperation from services in the Trust | Nahida Rahman
SAR Compliance | 10% overdue | 0% overdue (100% SLA) | Business as usual | Business as usual | Figures for overdue cases (over 30 days or beyond extension) | Saves potential costs (through penalties) and improves efficiency | IROs and IGMs | AA and DH
SAR Templates and Internal processes | Update templates | Create and send internal processes | Business as usual | Business as usual | Case workers to use new templates and follow processes | Will assist in improve the efficiency of individuals answer SARs requests, promotes professionalism | From the DPO, IGMs and Caseworkers | AA and DH
SARs Team Development | Training and development needs identified and discussed at appraisal | Training and development needs commenced | Business as usual | Business as usual | Team members attending and completing training | Will improve team performance and morale | The team members to go on training | AA & DH