## Slide 1
Newham CHS 2024/25
Annual Plan Priorities
Improved Population Health
Improved Experience of Care
Improved Staff Experience
Improved Value
Trust Strategic Objective
Priority areas for the service
Optimising flow through Community Trust pathway 2 inpatient facility and transfer of care hub
Improve access, waiting times, through co-production and pathway redesign with users and carers
Partnership working
Integrate IDH at ward level
Establish a clearly defined and communicated admission criteria to East Ham Care Centre, underpinned by National Discharge and Choice Policy to improve utilisation
Embedding good practice in line with National Discharge Policy and Guidance
Address podiatry backlog and maintain 18-week RTT
Address MSK access and transform pathways as part of Community Collaborative
Deliver continence and diabetes service within 18/52 RTT
Redesign EPCT services, amalgamating fast falls, rapid response and referral and assessment team into one "Urgent Community Response Team"
Achieve a 7/7 day working for therapies in EPCT and RR
Work with the community collaborative to address specialist pathways to manage waiting times in collaboration with the ICB and other providers
Develop integrated pathways between secondary and primary care and local authority (including virtual wards, frailty, telehealth, homelessness, neuro rehab, phlebotomy)
Defined workstreams / projects / programmes for 24-25
Deliver Financial Viability plans
Development of PIDS for Financial Viability programmes of work
Ensure that services are delivered in line with commissioning and financial envelope
Progress Fuller and PCN model
PCN transformation projects in line with Primary Care objectives
Deliver services within commissioning frameworks
Review service specifications particularly focusing on Long Covid and Pulmonary Rehab
Review the falls clinic/pathway currently provided in the Rapid Response team
Urgent and Emergency Care
ACP development within EPCT
Psychology input into household patients
Point of care testing and confirm a go-live date/rollout
Rapid response and falls to be one team
Streamline ordering of diagnostics
Emergency Department front door integration
Co-design UEC and ICT service in collaboration with Community Collaborative and ICB
Workforce, Recruitment and Retention plans
Increase uptake on apprenticeship roles in AHP and nursing by 5%
Collaborate with schools and colleges
Embed safe staffing tools and report quarterly ensuring that staffing models reflect the acuity and dependency of patients
Develop a workforce pipeline for international professionals linked to agency reduction (10% reduction)
Rotation posts for AHP with LBN and Acute
Realign admin functions away from clinicians ensuring skills and competencies are mapped for all bands and monitored
Sustainability
Promote paper-light and agile working through the rollout of laptops
Repatriate services to East Ham Care Centre to maximise areas
Reduce footfall of multiple providers in patients homes (transport, IT)
Maximise estates and review open space usage

## Slide 2
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | How does this link to your FV/ Sustainability goals | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  |  | 
Urgent and Emergency Care | Review service specification with the ICB and develop ED front door links with NUH Work with the ICB to design the URC model in line with national and NEL needs | Audit patient activity for point of care testing and map patient journey to ascertain whether current test panels are effective | Business as usual | Business as usual | Increase in oral antibiotic prescribing Reductions in ED admissions | Supporting admission avoidance which will improve patient experience | Pharmacy ICB ED | Raj Shah
Progress Fuller and PCN model | Ensure effective communication between ICS subgroups at place levels | CD to feedback to CS forums as work progress in Transformation groups | Business as usual | Business as usual | TBC | None identified | None identified | Raj Shah
Partnership Working | EMIS templates update and scoping exercise of respiratory virtual wards – audit current activity and demand against current staffing model New Florence system evaluation and Docobo within care homes Pathway meeting with stakeholders and funding identification for homelessness Neuro-navigator funded and identify training needs and gaps Review phlebotomy and feedback to staff Approve funding for frailty | Respiratory virtual ward live and potentially frailty virtual ward Care homes pilot and scaling where RMT need is identified Develop a sustainable place based model for homelessness – dependent on ICB funding Continue discussion with ICB and identify IC set up to provide care to L1 patients including staff training needs and review neuro-navigation data Barts to liaise with contracts after pilot | Evaluation and data collection Relevant SLT and MoUs to implement | Develop a business case if applicable for telehealth and level 1 patients – neuro rehab Business as usual | Analyse data via discharges and step downs Swiftqueue Audit patient activity Feedback and patient surveys Outcome data | Reducing pathway duplications Streamlining current pathways ensuring these are effective and efficient contributing to patient outcomes | LBN ICB Finance BDU Performance | Ram/Jo/Gavin
Optimising flow through community trust pathway 2 Inpatient facility and transfer of care hub | In reach therapy impact and data collection, review and meet with NUHT therapists to integrated IDH at ward level Agree an admission and discharge criteria | Implement recommendations from Q1 review | Evaluation against current workforce and possible A and E in reach inclusion (capacity dependent) | Continue and review data and presnet at IDH governance group | In reach data and measurement against actual discharges – to be led by the head of IDH | Establishing a clear admission and discharge criteria to prevent delays, admissions etc. | In reach data with the help of performance as required | Ram

## Slide 3
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | How does this link to your FV/ Sustainability goals | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  |  | 
Improve access, waiting times, through co-production and pathway redesign with users and carers | 3% reduction in podiatry caseload Ensure referral guidance is in place for MSK Undertake demand and capacity analysis for Diabetes/continence People and culture consultation for 7/7 working in EPCT and RR | 5% backlog reduction in podiatry caseload Review the clinical effectiveness of the getUbetter app for MSK GP/PCN engagement to ensure effectiveness of diabetes and continence Start process with People and Culture for EPCT and develop business case | 10% reduction in backlog for podiatry Business as usual Consultation for EPCT services | Business as usual | Waiting times (referrals, waiting lists etc.) KPIs Activity growth Staff wellbeing via. Surveys | Enusring services remain efficient reducing delays and reducing costs by ensuring that patients are moving through the pathway efficiently | Performance Digital ICB Barts Health People and Culture Primary Care Finance | Gavin/Jo/Ram
Workforce, recruitment and retention plans | Appoint AHP facilitator Ensure Band 8a/7 training for Safe Staffing Scope out increasing update of AHP apprentice roles | Advertise AHP apprentice roles Implement safe staffing training | Business as usual | Business as usual | Retention of staff Increase temporary staffing to backfill vacancy created by post Staff survey Evaluation against current workforce | n/a | Governance team Psychology Corporate People and Culture | Gavin/Ram/Jo
Deliver services within commissioning frameworks | Service conitnuity of long covid Book additional value for pulmonary rehab classes Review falls clinic/pathway | Potential tender process for long covid Consider PR/CR/LC ops service merger and leadership direction | Potential service provision across NEL for long covid Review services' activity and data reporting in line with national requirement | Development of a business case for pulmonary rehab | Referral data Patient feedback | Ensuring services meet FV goals and targets | Performance People and Culture | Ram
Sustainability | Move away from patient folders and current model of printing | Implement learning from Q1 | Business as usual | Business as usual | Printing volumes | Promoting paper-light and adult working through the rollout of laptops | Green Team | Fran Colley
Financial Viability | Conclude PIDS for Financial Viability programmes Conduct a consultation of services to relocate | Reduce phlebotomy staff in line with the review recommendations | Monitor activity Relocate services following office consolidation review | Business as usual | SQ data | FV Programmes of work | Sarah (FV) Performance SQ | Jo/Ram