## Slide 1
Primary Care 2024/25
Annual Plan Priorities
Improved Population Health
Improved Experience of Care
Improved Staff Experience
Improved Value
Trust Strategic Objective
Priority areas for the service
Further developing and maturing patient participation and engagement
Improving access to primary care
Increasing the number and range of directorate forums with patient representatives
Facilitate Patient Participation Groups (PPGs) membership to reflect practice/local population
Establish a network of ELFT PPGs to support shared learning and increased impact
Increase the number of practices that are Service User accredited
Increase impactful use of technology including e-consult and cloud telephony
Increase the effectiveness of Care Navigation and Triage processes
Ensure patient education with Patient Participation Groups (PPGs) to manage access
Ensure full use of Additional Roles Reimbursement Scheme (ARRS) and other Primary Care Network (PCN) resources
Defined workstreams / projects / programmes for 24-25
Identifying and reducing health inequalities and ensuring equitable outcomes
Identify and reduce health inequities with targeted projects at each practice
All practices to attain accreditation including Safer Surgeries and Veteran Aware
Improving team and individual staff wellbeing and development
Create a modern primary care workforce strategy to include recruitment and retention, health and wellbeing, pipeline/succession planning and continuous professional development (CPD)
Focus on team and organisational development
Enable leadership development for practice managers and clinical leads
Improving integration and system influence
Further develop system and community partnerships to integrate care
Establish a Homelessness & Inclusion Network/Board across ELFT to better include the ICB and regional thinking or planning
Providing compassionate, trauma informed primary care
Facilitate team training on Trauma Informed Care (TIC) and reinforce this with reflective practice
Leading and delivering national innovation and research in primary care
Establish an internal research and innovation infrastructure
Pursue funding for initiatives and their evaluation
Improving financial sustainability: income generation and best use of available resources
Undertake a structured review of primary care expenditure and income
Capitalise on economies of scale through:
  Procurement
  Standardised processes and information management
  Maximise income streams through targets and performance achievements (Quality outcome framework, investment and impact fund, local enhanced service etc.)
  Review pricing and process to secure income from non-NHS work

## Slide 2
 | Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | What support is required to achieve this priority? | Accountable lead
 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  | 
Improved Population Health | Identifying and reduce health inequities and ensure equitable outcomes | Practice level focus agreed based on local need & data | Work to secure accreditation and to address inequalities will have commenced with accountability and oversight | Feedback and other data will be used to understand progress , impact and pace of change | Feedback and other data will be used to understand progress , impact and pace of change and inform 24/25 plans | Core 20 plus 5 metrics are contractual requirements to measure population health outcomes. For example, PCN DES, IIF and QoF achievements | QI coaching JSNA and other relevant data | Medical Director Head of Nursing
 | Improving access to primary care | Demand and capacity well understood | Structured work streams using QI in place and increasing uptake of e-consult, appointment avoidance and triage | % improvement TBC | % improvement TBC | Increase in population uptake Timely access to appointments Patient feedback | Reliable visible comparable data Clinical Leadership Up to date awareness of local resources Quality Improvement | 
 | Improving system presence, influence & integration | Undertake a stakeholder and forum mapping to establish relationships at MD/DoS level for each geography Commence CMC-CMH project as a test case Participants identified and inaugural session held | Initiate consensus re: areas of mutual benefit and possibilities for collaboration/ change TORs including priorities drafted | Emerging plans, ensuring that quarterly meetings are in place | Develop plans and delivery with ongoing quarterly meetings to monitor progress | Patient feedback (PREM, FFT, GP, PS) | Capacity and resources Improved integration of Primary Care directorate with the Trust | Service Director Medical Director
Improved Experience of Care | Further developing/ maturing patient participation & engagement | Detailed work plan including training agreed and discuss at DMT to agree a recruitment campaign with PPG leads. Ensure quarterly/bimonthly sessions are scheduled | Implementation of detailed workplan and progress discussed a routine forums. Ensure 2 practices are SU accredited | Business as usual, ensuring that regular forums are ongoing. | Business as usual, ensuring that regular forums are ongoing. Ensure that 4 practices are SU accredited | Patient feedback (PREM, FFT, GP PS) % forums with patient representation No. SU accredited practices | Capacity and resources Quality Assurance | Medical Director PP Lead Quality Assurance
 | Providing Compassionate , Trauma Informed Primary Care | Training and facilitator resource in place | 25% practices TIC training and accessing RP | 50% practices TIC training and accessing RP | 75% practices TIC training and accessing RP | Staff satisfaction survey / wellbeing measure Patient feedback (PREM, FFT, GP PS) | Capacity and resources | Service Director Medical Director

## Slide 3
 | Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | What support is required to achieve this priority? | Accountable lead
 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  | 
Improved Staff Experience | Improving team and individual staff wellbeing and development. (Developing a strategy for 0-5 years including) Recruitment and retention of diverse MDT Health and wellbeing Progression and succession planning | Understanding of the directorate workforce pressures. Articulate a clear vision for our workforce using baseline data to identify gaps Identify Individual development needs and resources required | Draft plan based on scoping undertaken in Quarter 1, to be taken for consultation | Strategy in place | Business as usual with regular monitoring and oversight of plan in place | Staff satisfaction survey Reduction in agency spend Reduction in sickness absence, turnover and ER Increased SLT capacity as less 'acting down' | Capacity Resource to fund CPD | Medical Director Service Director Head of Nursing Assistant Director People & Culture
Improved Value | Improving Financial Sustainability: Income Generation & Best use of available resources | Undertake a review to address economic variance and identify opportunities and quantify opportunities for efficiency at directorate and regional level. Update costs and rollout car machines, changing SOP. | Agree and implement a revised process, including a standardisation and review of areas where there are wasteful processes | Routine review and delivery of progress against financial viability plans | Routine review and delivery of progress against financial viability plans | Reduced overspend Efficient processes increasing staff satisfaction and reduced waste Increased income Lean, efficient GPSU model to replicate | Expertise in primary care finances | Service Director Finance Team Business Development
 | Leading/ delivering national innovation and research in primary care | Academic in post | Research vistion articulated with implementation plan | TBC | TBC | Patient feedback (PREM, FFT, GP PS) % forums with patient representation No. SU accredited practices | Support from wider Trust teams on various aspects of delivery eg Data, existing academic forums | Medical Director