## Slide 1
Quality Assurance
2024/25 Annual Plan Priorities
Improved Population Health
Improved Experience of Care
Improved Staff Experience
Improved Value
Trust Strategic Objective
Priority areas for the service
Equity and Inequalities
Promote and Strengthen the of Patient Experience Feedback
Creating a assurance offer for Corporate Services
Getting the basics right
Moving from participation to insight
Equity and Inequalities work – details TBC
To test ways of improving the collection of patient experience feedback and it’s use in improvement
Work with other corporate services to develop our corporate offer and find out where we can have most impact
To test and implement a Stakeholder Led Accreditation process for corporate teams
Ensure the QA team has a clear purpose, objectives that are measurable and processes. Ways of communicating help the team achieve its objectives
Complete InPhase implementation and realisation of benefits including triangulation and action monitoring. Support services to make the most of the platform
Test opportunities to share cross-directorate learning from QA workstreams
Defined workstreams / projects / programmes for 24-25

## Slide 2
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  | 
Getting the basics right | Design and embed feedback processes – collection, review and response Establish space to review team data Develop customer service charter | Develop standardized induction plans for each QA team role |  |  | Feedback about QA team Key performance metrics e.g. participation data |  | Ellie / James
Patient Experience Feedback | Deliver training/teaching so staff are comfortable using Civica and Power BI dashboard Test ideas to promote patient experience feedback collection in City and Hackney | Insight reports to be embedded in DMTs Provide examples of good practice Develop and finalise Patient Experience bundle |  |  | No of responses collected per month No of teams participating |  | Selina
InPhase implementation | All QA modules are live on InPhase and in use. | Help teams use InPhase to develop and track actions Map governance processes for action monitoring Speak to teams about the benefits | Test adding ward based audits and checklists to InPhase |  | No of teams using InPhase to track actions No of overdue actions |  | Ellie
Corporate accreditation | Test programme with 3 teams and evaluate Recruit Assessors | Launch programme for all corporate teams and promote |  | Evaluation of impact and shared learning event | Feedback about the process No of teams participating No of assessors involved |  | Ella