## Slide 1
Quality Improvement Department
2024/25 Annual Plan Priorities
Improved Population Health
Improved Experience of Care
Improved Staff Experience
Improved Value
Trust Strategic Objective
Priority areas for the service
Pursuing Equity
Flow programme
Building Capability
Financial Viability
Multiyear programme to support teams across trust to address inequalities and inequity in health outcomes, experience and access to care. Teams include improving equity around, race, gender, LBGTQ+, disability, Ensure Service user involvement.
Conclusion of a year-long programme that supported teams across the Trust to use QI methods to approach improving inpatient safety and quality of care. This includes inpatient flow, safety bundle and therapeutic engagement & observation. Ensure Service user involvement
Alignment of QI training with directorate priorities​
Pocket QI, Improvement Leaders programme, Improvement Coaching Programme . Service users
Identifying and addressing inequalities of access to QI training programmes. Support and develop QI team and ICS team
Supporting the rigorous use of Improvements methods for Trust wide improvement work
Supporting QI coaches' development. QI coaches with Lived experience
QI support using improvement methods for financial viability
Defined workstreams / projects / programmes for 24-25
Annual plan for 2024-25: Team/service: Quality Improvement

## Slide 2
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  | 
Pursuing Equity ​ (population Health, Staff experience, Service user experience) ​ | Launch of Year 2 Pursuing Equity ​programme Recruitment of teams ​ | All teams started testing​ Measurement plan in place ​ | Improvement​ Sustained improvement ​ | Improvement​ Sustained improvement ​ | Number of teams ​ % of teams testing​ % of teams seeing improvement​ % of teams with service user involvement​ *specific measures for each topic area​ | Executive sponsor. People participation. Communications. Trust Networks. | Head of Improvement Programmes
Capability ​ (staff experience) ​ | ILP - Wave 13 complete​ ICP – cohort 8 complete​ Pocket QI monthly ​ | ILP - Recruitment for wave 14 ICP – Recruitment for cohort 10 Pocket QI monthly ​ | ILP - Commence wave 14 ​ ICP – commence cohort 10​ Pocket QI monthly ​ ​ | Support project leads with Projects on ILP ​ Pocket QI monthly ​ ​ | Pocket QI - Number of graduates ​ ILP– Number of graduates​ ICP – Number of graduates ​ Number of active coaches across the Trust ​ | Logistic support and venues. Communications . People Participation. | Head of Improvement Capability
Flow​ (service user experience) ​ | Designing the Flow programme across inpatient units. ​ Launch. ​ | All teams testing and measuring. ​ | All teams testing and measuring. ​ | All teams testing and measuring. ​ Collating lessons and forward planning. ​ | Number of teams ​ % of teams testing​ % of teams seeing improvement​ % of teams with service user involvement​ *specific measures for each topic area​ | Executive sponsor . Director of Nursing. Communications. Performance. People Participation. | Associate Director
Value ​ (Improving value)​ | Support FV to identify FV QI projects ​ | Support FV to identify FV QI projects ​ | Support FV to identify FV QI projects ​ ​ | Support FV to identify FV QI projects ​ | Number of FV projects across Directorates​ ​ Total cost savings within Internal dept ​ | Finance business partners. | Associate Director