## Slide 1
Tower Hamlets CHS 2024/25
Annual Plan Priorities
Improved Population Health
Improved Experience of Care
Improved Staff Experience
Improved Value
Trust Strategic Objective
Priority areas for the service
Improve access, waiting times, through co-production and pathway redesign with users and carers
Partnership working and development of integrated pathways
Implement the Foot Health review recommendations and action plan
Review the need and benefit of seven day a week provision for therapies in community and Urgent Community Crisis Response pathways
Progress with Community Therapies QI project on waiting times
Review referral pathways into services and develop and implement service models that minimise delays
Work with community collaboratives to address specialist pathways to manage waiting times
Re-commissioning of GP Alliance Contract with ELFT, GPCG. 2024/25 Contract transformation and re-commission by November 2025
Work with Tower Hamlets Place to establish an Intermediate care working group and Intermediate Care Board which reports to the THT Board
Collaborative working with partners to improve communication between GPs and Community Health Services
Progress with frailty ward development within NEL framework
Maximise the independence of people with Diabetes
Redesign pathways between TH Learning Disabilities Team and TH CHC Team
Achieve reduction in care package cost for TH residents on the discharge to assess pathway through using Optimal Handed Cre principles
Review and redesign End of Life pathways for TH residents
Defined workstreams / projects / programmes for 24-25
Deliver Financial Viability plans
Change ways of working in EPCT District Nursing Services, Rapid Response, Intermediate Care, Triage and Assessment Team, Rapid Response and Falls Teams
PCN Development
Contribute to the TH place development of a neighbourhood model
Deliver services within commissioning frameworks
Have outcomes for each service that demonstrate the impact of service user outcomes
Undertake patient flow mapping between TH services
Urgent and Emergency Care
Ensure reactive care access to Rapid Response and Falls service to avoid inappropriate conveyance or admission
Ensure proactive care in Care Homes
Rollout Point of Care testing
Co-design UEC and ICT service in collaboration with the Community Collaborative and ICB
Workforce, Recruitment and Retention plans
Increase uptake on apprenticeship roles in AHP
Embed safe staffing tools and report quarterly ensuring that staffing models reflect the acuity and dependency of patients
Develop a workforce pipeline for international professionals linked to agency reduction
Explore rotational posts for AHP with Royal London
Support staff wellbeing with the SAFER QI project to provide support to staff who experience violence and aggression
Support staff wellbeing by embedding trauma informed management and Schwartz
Map competencies for all bands, ensuring consistent management skills for Band 7 and above
Reduce agency and bank usage
Workforce planning to be embedded at DMT level
Sustainability
Promote paper-light and agile working through the rollout of laptops and reduce carbon footprint

## Slide 2
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | How does this link to your FV/ Sustainability goals | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  |  | 
Urgent and Emergency Care | Liaise with Care Home managers and GPs around reactive care and access to RR as well as proactive care in Care Homes Pilot and testing of point of care testing | 2% increase of referrals to rapid response/falls pick up 100% of Care Home MDTs that took place in the quarter, 90% residents on insulin reviewed Implementation of Point of Care | 3% increase of referrals to Rapid Response/Falls pick up 100% of Care Home MDTs that took place in the quarter, 90% residents on insulin reviewed Evaluation of point of care | 4% increase of referrals to Rapid Response/Falls pick up 100% of Care Home MDTs that took place in the quarter, 90% residents on insulin reviewed Business as usual PoC | Performance KPIs = no. Referrals RR/Falls % of residents on insulin and reviewed quarterly % of Care Home MDTs that took place | Improve engagement with care homes to help streamline pathways Rollout of point of care will require EMIS template to be update to improve processes and reduce delays | N/A | Alex Hadaya Petra Nittel
PCN Development | Participate in relevant meetings and activities including mapping and pathway design | Attend meetings | Attend meetings | Attend meetings | Attendance at meetings | n/a | None identified | Alex Harborne Petra Nittel
Partnership Working and development of integrated pathways | Establish joint business planning processes for CHS via engagement with ICB and THT planning rounds Sourcing a ToR and strategy documents on intermediate care delivery from other providers Establish GP QI project to improve communication Draft SOPs for integrated pathways around End of Life, Learning Disabilities and long term conditions | Develop SOP and MoU for joint working and monitoring all quality and performance indicators KPIs to support joint delivery Agree on pathway for EMIS template change and timeline for control management meetings Improve communication and aspire to 10% increase in website views and keeping rejected GP referrals under 20% for continence and foot health Record one more podcast Agree SOPs and implement Reduce unplanned visits by 2% and increase night sitting activity by 2% | Establish workstream transformation programmes with the ICB 10% increase in website views and maintaining under 20% of rejected GP referrals for continence and foot health Record one podcast with GPs PSDA design and implementation and reduction of refused medication incident reports by 3% 2% improvement in care package provision against comparative quarter | Continue with workstream transformation programmes Maintain website views around 10% above average, record one more podcast Hold incident learning event with primary care and keep rejected referrals from GPs under 20% for continence and foot health Pathways in place that support client group with identified needs Reduction in unplanned visits between 8pm-8am | All service KPIs sitting in TH Community block contract Website views Number of podcasts recorded Rejected GP referrals into Continence and Foot Health Number of collaborative incident meetings taking place Increase use of GP EMIS template in primary care % of refusal of medication indicts % reduction of number of patients on caseload requiring insulin injection % reduction in care package provision against 23/24 baseline % increase of TH residents receiving nigh sitting as part of carer's respite % decrease of injected analgesia four times a day % increase of syringe driver use | Reduces the number of repetitive requests for changes to EMIS forms which is a burden on admin staff time and adds to workload Establishing collaborative working groups with providers to reduce nurse call out activity, reduce care package provisions and management of stakeholder interests, reducing the time it takes to reach a decision. | Contracts Finance ICB Quality Team GP Care Group CEG Barts CHS ELFT Director of Safety NEL Quality Teams | Alex Harborne Petra Nittel Emma Robinson Nike Bademosi
Improve access and waiting times | Introduction of new timelines within Foot Health PSDA cycle for 7 day EPCT working Review triaging process to exclude duplicated entries on waiting lists (Physio/OT) SOP in place for ED/Transfer of Care Hub | Evaluation and review of timelines in Foot Health PSDA evaluation of 7 day working in EPCTs PDSA evaluation ensuring that 60% of referrals triaged as urgent care are seen within 15 days from receipt of referral 0% delay for referrals from AAT in ED, 0% delay for referrals from Transfer of Care hub | Evaluation and review of Foot health timelines. 7% increase in emergency slots attended against 2023/24 Ensure 75% of referrals triaged as urgent care are seen within 15 days Implementation for ED/Transfer of Care Hub | Business as usual with Foot Health slots and a 10% increase in emergency slots attended 80% of referrals triaged as urgent seen within 15 days Evaluation of Transfer of Care Hub | % increase in attendance of emergency slots in TH Satisfaction scores Reduction in therapy waiting list by 10% Feedback from families Reduction of cancelled appointments for assessment by 10% % of referrals triaged as urgent seen within 15 working days from recept of referral 10% in self-referrals 25% decrease in time from referral to receipt in TH CHS services | Maximise effectiveness of appointment slots within the service, helping to reduce waste and reducing DNA rates | People and Culture TH CHS Management Primary Care Communication Team Performance Team Contracts Team | Petra Nittel

## Slide 3
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | How does this link to your FV/ Sustainability goals | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  |  | 
Workforce, Recruitment and Retention Plans | Scope feasibility of AHP apprentice roles Complete audit from safer staffing tools and report 100% international recruits trained and in post Safer QI project team meeting regularly with data collection taking place to test testing in Triage and Assessment team EPCT culture review and recommendations implementation Relaunch of monthly TIC training Review of establishments against caseload Prepare audit of work life balance | Audit of safer staffing tools to be completed and results reviewed Start testing SAFER assessment in Triage and Assessment with 3 times a week data collection to monitor improvement At least one Schwartz round to have taken place – evaluation and design to inform the next one 90% of attendees to rate training as highly relevant/useful to their role and a 10% increase in nursing completion of training 25% of roles added into repository and skills and competence mapped 10% improvement in agency reduction and bank usage 85% completion of induction and work life balance audit discussed at QAG | Review data in Triage and Assessment – 10% increase in SAFER scores First audit of staff who have completed training: % of staff rating ongoing relevance and usefulness of TIC in their practice At least one Schwartz round to have taken place – evaluation and design to inform the next one 50% of roles added into repository and skills and competence mapped 15% improvement in agency reduction and bank usage 90% completion of induction and work life balance audit discussed at QAG | If measurable improvement, consider implementing SAFER assessment and SAFER workplace pathway across TH CHS Second audit of staff who have completed training At least one Schwartz round to have taken place – evaluation and design to inform the next one 100% of roles added into repository and competence mapped 25% improvement in agency reduction and bank usage 95% completion of induction and work life balance audit discussed at QAG | SAFER scores in triage and assessment Violence and aggression incidents Overall number of staff attending training sessions Staff ratings of relevance and usefulness of TIC training to their roles Number of Schwartz rounds undertaken % of roles mapped % of new starters who complete induction in quarter % of staff who have had a discussion with their manager about flexible working % decrease in agency/bank expenditure | Reduction in agency spending Mapping staff according to skill mix to ensure effective delivery and identify gaps in workforce | Finance Lead Temporary Staffing Team QI People and Culture | Sharen Hayre Alex Harborne Nike Bademosi Eleanor Mata
Deliver services within commissioning frameworks | Workshop and clinical summit to take place across all CHS directorates | Staff training and monitoring 50% outcomes and KPIs completed Workshop | 60% outcomes and KPIs completed Workshop | 70% outcomes and KPIs completed Workshop | Increase in completion of outcome measures Completed mapping document | n/a | None identified | Petra Nittel
Sustainability | Monitor uptake of laptop rollout Promote the use of MS Teams for storage of documents Reduce rooms lit by 2% | 60% of staff start their working day by directly going to their visit and going home after visits Promote the use of MS Teams for storage of documents Reduce rooms lit by 3% | 70% of staff start their working day by directly going to their visit and going home after visits Promote the use of MS Teams for storage of documents Reduce rooms lit by 4% | 80% of staff start their working day by directly going to their visit and going home after visits Promote the use of MS Teams for storage of documents Reduce rooms lit by 5% | % of staff who do not need to come to the office at the beginning of the day and end of their working day % improvement of reduction of empty rooms lit against spot audit in February 2024 | Sustainability plan for 2024/25 | None identified | Petra Nittel Fran Colley
Deliver Financial Viability Plans | Write PIDs for Financial Viability programmes of work and communicate these with staff and managers | Reduction of duplicated care episodes (Rapid Response and Triage and Assessment) by 2% Implementation of new ways of working within Rapid Response and Falls teams | Reduction of duplicated care episodes (Rapid Response and Triage and Assessment) by 3% Monitoring progress of financial viability schemes | Reduction of duplicated care episodes (Rapid Response and Triage and Assessment) by 5% Monitoring progress of financial viability schemes | Reduction in EPCT locality caseloads by 5% Reducton of duplicated care episodes by 10% Release of posts | Financial viability plan for 2024/25 | None identified | Nike Bademosi Eleanor Mata Alex Hadayah Petra Nittel