## Slide 1
Tower Hamlets MH
2024/25 Annual Plan Priorities
Improved Population Health
Improved Experience of Care
Improved Staff Experience
Improved Value
Trust Strategic Objective
Priority areas for the service
Managing and continuing with current community transformation, learning disability and sustaining inpatient Mental Health care
Improve the experience of care by moving towards prevention and continuity in services across Tower Hamlets Mental Health Services in Tower Hamlets
Working towards meeting financial viability and sustainability targets
Create a pilot and identify a base for a Community Mental Health Centre that becomes a Single Point of Access for that neighbourhood that is open 24 hours a day
Embed and enhance the crisis function, guest beds, home treatment, pharmacy, psychology, benefits, housing, social care into the Community Mental Health Centre, Third sector involvement
Reduce the number of beds needed for inpatients in this locality
Write operational policies or a standard operating procedure to support the establishment of a Community Mental Health Centre
Identify and recruit staff to work in the Community Mental Health Centre, alongside the development of an articulated staffing model
Working across Tower Hamlets to reduce mental health stigma and inequalities of access, particularly collaborating with the Third Sector
Working with Tower Hamlets community to increase understanding of the proposed model for patients and staff
Staff in the Tower Hamlets community to visit Trieste in January 2024 and further understand the model
Focus on strengthen Safety culture (DNAs, Suicide Prevention and Observations)
Increase focus on community services
Ensure more connected working with wider community services
Support transitions of complex patients to community services
Directorate safety improvement plan for community, learning disabilities and the inpatient services, undertake a thematic review of serious incidents and action plans
Embed the Intensive Support Team (IST) in learning disability services
Undertake a review of supported living accommodation
Increase the number of bed sales across Tower Hamlets to other organisations by reducing bed use through spot purchasing
Focus on initiatives that reduce environmental impact including medications
Review service alignments and embed in Community Mental Health Centres (Crisis, Home Treatment Teams, Psychology)
Remote Measurement Technology (RMTs) protocol and arrangement to be in place
Defined workstreams / projects / programmes for 24-25
Managing and maintaining the current community learning disability priorities
Development of the Learning Disability partnership board
Supporting people with learning disabilities to live locally which includes the increase in local supported living resource and Shared Lives
Continue with the Population Health and Obesity QI/Triple Aim work
Improving the Transition experience for young people transitioning to CLDS by improving flow across the pathway

## Slide 2
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | Sustainability/FV | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  |  | 
Managing and continuing with current community transformation, learning disability and sustaining inpatient Mental Health care | Staff in the TH Health community to visit Trieste in January 2024 and further understand the model Identify a bed and refurbish for the Community Mental Health Centre (CHMC) Embed and enhance the crisis function, guest beds, home treatment, pharmacy, psychology, benefits, housing, social care into CMHC, 3rd Sector Safety culture (DNAs, Suicide Prevention and Observations) | Identify and recruit staff to work in the Community Mental Health Centre alongside an articulated staffing model Write operational policies or standard operating procedure to support this new way of working | Create a pilot community mental health centre that becomes a Single Point of Access for that neighbourhood that is open 24 hours a day Work across Tower Hamlets to reduce mental health stigma and inequalities of access Reduce the number of beds needed across inpatients for this locality | Work with the Tower Hamlets community to increase understanding of the proposed model for patients and staff so that it becomes a business as usual process | E.g. reduce length of stay by X... Time between admissions (to measure of prevention) Reducing number of high intensity users being admitted (complex services) Improved DNA/reduction Suicide across services, 72 hour follow-up Reducing LOS – moving longest stays back to community | Reduce OAP Reducing medication usage Reducing travel by seeing people seeing people closer to home/virtually | IT and Digital – establish new ways of capturing data on RiO and reduce the time spent on manual paperwork Staff movement consultation (People & Culture) Project management and freeing up senior clinicians and management time to engage in the process – (Organisational Development support) Business Development Local engagement with communities – Third Sector funding Estates – building and soft and hard facilities management | Day/Leah/Dadai/Marion
Improve the experience of care by moving towards prevention and continuity in services across Tower Hamlets Mental Health Services in Tower Hamlets | Increase focus towards community services ensuring more connectedness with wider community services – developing through MH Partnership Board through a dedicated communication strategy Support transitions of complex patients to community services Directorate safety improvement plans for community, LD and inpatient services – undertake a review of Serious Incidents and action plans Embed Intensive Support Team in Learning Disability Services Review of supported living accommodation – contracts and pathways | •Directorate Learning Lessons sessions •Increase resources in the resettlement team to focus on moving patient on in supported schemes •Red to green initiative in inpatient wards •Suicide and observations specific sessions in SMC meeting •Refocus on SMI population to prevent admissions •Recruitment to fill all community based vacancies •Reduce occupancy of inpatient beds to 85% •Improve discharge pathways with local partners (homeless, NRFP, NFA) | Q1 Priorities to be Business as usual | Q1 Priorities to be Business as usual | e.g. % of service users known to community teams reducing their occupied bed days usage Reducing waiting times and waiting lists Measuring the impact of psychoeducation and inreach to hard to reach communities, raising the awareness – working closer in communities and number of sights Intensive LD – how many service users seen, how can many return to community Number of closed SI Action plans and learning lesson sessions with partners Length of time to moving into supported accommodation | Private beds/income generation | Training for the new PSIRF processes Training and development with wider TH-based providers Commissioners input on supported accommodation | Day/Leah/Dadai/Marion

## Slide 3
Priority/ Key Objective | Where do we expect to be by... |  |  |  | What performance measures will be monitored? | Sustainability/FV | What support is required to achieve this priority? | Accountable lead
 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  |  | 
Working towards meeting financial viability and sustainability targets | Increase the number of bed sales across Tower Hamlets to other organisations by reducing bed use through spot purchasing Focus on initiatives that reduce environmental impact including medications Remote Measurement Technology (RMTs) protocol and arrangement to be in place | Review service alignments and embed in Community Mental Health Centres (Crisis, Home Treatment Teams, Psychology) |  |  | Number of OAPs and spot purchases | Income | Support with contracts/spot purchases – BDU and Finance input Support identifying sustainability projects – Green Plan | Day/Leah
Managing and maintaining current community learning disability priorities | Development of the Learning Disability partnership board Supporting people with learning disabilities to live locally which includes the increase in local supported living resource and Shared Lives Continue with the Population Health and Obesity QI/Triple Aim work Improving the Transition experience for young people transitioning to CLDS by improving flow across the pathway |  |  |  |  |  |  | Mary Marcus Nicole Eady